# Benchmark no. 2.5

Implementation of the Strategic Plan started

Benchmark prepared by:

Pavel Sřemer (CZ) – OZV CEI Directorship, Prague, BC Project Leader

Olga Klašterková (CZ) – CEI Directorship, Project coordinator

Rob Bakx (NL) – InfoMil, RTA

Date: 3 June 2005

## Implementation Strategic Plan started

After its approval on 1 December 2004 the implementation of the Strategic Plan of the Czech Environmental Inspectorate (CIZP) was started. This benchmark document shows the list of strategic goals and objectives to be fulfilled. In the Strategic Plan for each of the objectives a deadline was set.

The overview in this benchmark document shows which of the objectives have been met already, of which the implementation has started and of which the implementation has not yet started. Given the deadlines set in the Strategic Plan it will be obvious that there are objectives of which the implementation has not yet started or which have not yet been fulfilled.

The fulfilled objectives are marked in green (in the utmost left column), the ones of which implementation has started are marked in yellow (in the middle column) and the ones of which implementation has not yet started are marked in red (in the utmost right column).

The evaluation date used to categorise the objectives in green, yellow or red was 23 May 2005.

The overall conclusion is that the implementation of the Strategic Plan of the CIZP has started.

#### Program goals

| Goal A.1 Ensuring a high level of environmental protection in the Czech Republic |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective A.1.1 |  |  | Limitation and prevention of pollution of the environment through integrated inspection in coordination with other competent bodies |  |  |
| Done | Started | Not yet started |  |  |  |
|  |  |  | - Evaluation of gained experience |  | 4th Q 2004 |
|  |  |  | - Proposal for new system of integrated inspections |  | 1st Q 2005 |
|  |  |  | - Realisation of new system of inspections |  | 4th Q 2005 |
| New system development is in -Plan for 2005: Assessment of current system is planned in 4.Q. 2005. -New system implementation is planned from 1.Q. 2006 |  |  |  |  |  |
| Objective A.1.2 |  |  | More effective prevention of serious accidents due to better cooperation with other bodies |  |  |
| Done | Started | Not yet started |  |  |  |
|  |  |  | - Analysis of current cooperation |  | 2nd Q 2005 |
|  |  |  | - Adjustment of the existing system |  | 4th Q 2005 |
|  |  |  | - Enlargement of network of cooperating bodies and organisation |  | 4th Q 2005 |
| Analysis will be finished in time |  |  |  |  |  |
| Objective A.1.3 |  |  | Prevention of the creation of waste due to the cooperation with other bodies and organisations (including the ones from abroad) during TFS activities |  |  |
| Done | Started | Not yet started |  |  |  |
|  |  |  | - Participation in common inspection projects |  | since 2004 |
|  |  |  | - Participation in internal network of inspection bodies |  | since 2nd Q 2005 |
|  |  |  | - Proposal for creation of a centre |  | 3rd Q 2006 |
|  |  |  | - Creation of the centre |  | 1st Q 2007 |
| Objective A.1.4 |  |  | Setting priorities of inspection activities by concentrating on installations with significant impact on the environment and on installations for which previous inspections found serious problems |  |  |
| Done | Started | Not yet started |  |  |  |
|  |  |  | - Analysis of the situation in line with MoE | 1st Q 2005 |  |
|  |  |  | - Priorities proposal | 2nd Q 2005 |  |
|  |  |  | - Discussion of priorities with co-operating organisations | 3rd Q 2005 |  |
|  |  |  | - Incorporation of priorities into the Plan of activities for the year 2006 | 4th Q 2005 |  |
| Goal A.2 Protection and prevention of the damage of nature |  |  |  |  |  |
| Objective A.2.1 |  |  | More effective territorial protection through inspections of areas under Natura 2000 |  |  |
| Done | Started | Not yet started |  |  |  |
|  |  |  | - Preparation of inspections | 2nd Q 2005 |  |
|  |  |  | - Pilot inspections | 3rd Q 2005 |  |
|  |  |  | - Full scope of inspections | 1st Q 2006 |  |
| Objective A.2.2 |  |  | Prevention of threats against biodiversity via inspections on handling of GMOs |  |  |
| Done | Started | Not yet started |  |  |  |
|  |  |  | - Build further on practical experience of ‘old’ EU states |  | 1st Q 2005 |
| Objective A.2.3 |  |  | Preventing the abuse of forest by more effective internal co-operation with the nature protection unit as well as through external co-operation with the state prosecutors, the police and bodies of the state administration of forest management |  |  |
| Done | Started | Not yet started |  |  |  |
|  |  |  | - Creation of a network of co-operating organisations |  | 2nd Q 2005 |
| Goal A.1.3 Increase awareness of the public and the inspected subjects about laws in the area of the environment and the need to comply with them |  |  |  |  |  |
| Objective A.3.1 |  |  | Creation and implementation of consistent communication strategy of the CEI |  |  |
| Done | Started | Not yet started |  |  |  |
|  |  |  | - Proposal of its interim parts (increase of co-operation with the public, communication with media, active introduction of the CEI activities towards the public) |  | 1st Q 2005 |
|  |  |  | - Creation and discussion of the strategy |  | 2nd Q 2005 |
|  |  |  | - Start of implementation |  | 3rd Q 2005 |
| Not yet consistent strategy |  |  |  |  |  |
| Objective A.3.2 |  |  | Better use of the function of the CEI in EMS and vice verse use of EMS to support inspection and enforcement activities |  |  |
| Done | Started | Not yet started |  |  |  |
|  |  |  | - Training of CEI inspectors |  | 2nd Q 2005 |
|  |  |  | - A part of inspection work |  | 4th Q 2005 |
| Objective A.3.3 |  |  | Dissemination of experience and CEI promotion with the help of lecture activity of the CEI staff |  |  |
| Done | Started | Not yet started |  |  |  |
|  |  |  | - Proposal for the lecture activity |  | 1st Q 2005 |
|  |  |  | - Step-by-step realisation |  | Since 2nd Q 2005 |
| Lecture activity is provided on request, list of lecturers exists, but overall proposal does not exist yet |  |  |  |  |  |

#### Goals and objectives concerning organisational development

| Goal B.1 More effective enforcement of the law through strengthening of feedback role of the CEI in the regulatory cycle (including competencies) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective B.1.1 |  |  | “Anchoring” (Establishing) of the CEI as a concerned body in selected procedures in the field of environment |  |  |
| Done | Started | Not yet started |  |  |  |
|  |  |  | - Analysis of the current situation and proposal of selected procedures |  | 1st Q 2005 |
|  |  |  | - Preparation of materials in the framework of commenting procedure concerning relevant law drafts |  | Continuously |
|  |  |  | - Commenting on the Act on the environment |  | 4th Q 2004 and further on |
|  |  |  | - Forecasted validity of the Act on the environment |  | 2nd Q 2006 |
|  |  |  | - CEI activity as a concerned body |  | Since the Act on the env. comes into force |
| Objective B.1.2 |  |  | More effective setting of the CEI competencies, their unification in individual environmental media through a possible elimination of decision-making about fees, collecting and enforcing of fines and by enlargement into other sectors (land protection, protection against noise and vibration etc.) |  |  |
| Done | Started | Not yet started |  |  |  |
|  |  |  | - Analysis of the CEI competencies |  | 1st Q 2005 |
|  |  |  | - Proposal of adjustment of the CEI competencies |  | 2nd Q 2005 and continuously within commenting procedures for individual laws |
|  |  |  | - Co-operation with the MoE on preparation of legal adjustments |  | 3rd Q 2005 |
|  |  |  | - Forecasted realisation of the new law adjustments |  | 2nd Q 2006 |
|  |  |  | - Application of new competencies |  | 3rd Q 2006 |
| Objective B.1.3 |  |  | Strengthening of the feedback role of the CEI in the regulatory cycle through more effective use of CEI comments in the legislation process based on its practical experience with enforcement of the law |  |  |
| Done | Started | Not yet started |  |  |  |
|  |  |  | - More quality commenting on laws with the aim to get better enforcement | Continuously |  |
| Objective B.1.4 |  |  | Getting feedback in the process of the environment protection through participation of the CEI employees in commissions working in the field of environment |  |  |
| Done | Started | Not yet started |  |  |  |
|  |  |  | - Analysis of the current state |  | 1st Q 2005 |
|  |  |  | - Proposal of more effective involvement in selected commissions |  | 2nd Q 2005 |
|  |  |  | - Dealing with relevant commissions |  | 3rd Q 2005 |
|  |  |  | - Normal full activity in individual commissions |  | 1st Q 2006 |
| Partial analysis done and partial involvement of staff in MoE commissions |  |  |  |  |  |
| Objective B.1.5 |  |  | More effective enforcement of the law through increasing of the level of legal tools used in the CEI |  |  |
| Done | Started | Not yet started |  |  |  |
|  |  |  | - SWOT Analysis of the current situation |  | 1st Q 2005 |
|  |  |  | - Proposal for improvement (including development of a strong internal legal service) |  | 2nd Q 2005 |
|  |  |  | - Realisation of proposals |  | 1st Q 2006 |
| Objective B.1.6 |  |  | Possibility to use other than sanction methods to support enforcement of the law in the inspection activity |  |  |
| Done | Started | Not yet started |  |  |  |
|  |  |  | - Analysis and proposal of methods |  | 4th Q 2005 |
|  |  |  | - Realisation of analysis results within commenting procedures on individual pieces of legislation |  | 1st Q 2006 |
| Objective B.1.7 |  |  | Support of more effective enforcement of the environmental law thanks to solution of the problem of uniform approach of first-line and second-line(appealing) bodies |  |  |
| Done | Started | Not yet started |  |  |  |
|  |  |  | - Submitting of solution proposals in the framework of commenting procedure on a new legislation |  | 3rd Q 2005 |
|  |  |  | - Co-operation with newly- established secod-lined body/serving as such a body |  | 2nd Q 2006 |

| Goal B.2 Professional organisation corresponding to the demands of the current time |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objective B.2.1 |  |  | Achieving the fulfilment of the EU minimum criteria for environmental inspections |  |  |  |
| Done | Started | Not yet started |  |  |  |  |
|  |  |  | - In depth analysis in cooperation with the Ministry of the Environment |  | 2nd Q 2005 |  |
|  |  |  | - Endorse measures to eliminate failures in the fulfilment of the minimum criteria |  | 4th Q 2005 |  |
|  |  |  | - Expected fulfilment |  | 1st Q 2006 |  |
| Internal start of analysis, not yet together with Ministry |  |  |  |  |  |  |
| Objective B.2.2 |  |  | Adjusting the structure of the inspectorates to the new demands of the integrated protection of the environment |  |  |  |
| Done | Started | Not yet started |  |  |  |  |
|  |  |  | - Evaluation of gained experience (including executed organisational change based on creation of expert sections) |  | 1st Q 2005 |  |
|  |  |  | - Proposal for new structure counting with bigger integration of the media and/or creation of a new structure according to the departments |  | 2nd Q 2005 |  |
|  |  |  | - Potential reorganisation of the CEI |  | 1st Q 2006 |  |
| Some evaluation done at chief inspectors meeting. Result: past organization changes meet the needs of CEI. Further integration may follow after evaluation of year 2005. |  |  |  |  |  |  |
| Objective B.2.3 |  |  | Creation of and co-operation in a national network of inspection and enforcement organisation in the area of the environment, co-ordinated by staff of the CEI |  |  |  |
| Done | Started | Not yet started |  |  |  |  |
|  |  |  | - Agreements on co-operation |  | 2nd Q 2005 |  |
|  |  |  | - Creation of the network |  | 4th Q 2005 |  |
| Czech IMPEL network for co-operation on EU level was created |  |  |  |  |  |  |
| Objective B.2.4 |  |  | Improvement of the internal communication in the CEI by the use of IT and through communication training and better workload management |  |  |  |
| Done | Started | Not yet started |  |  |  |  |
|  |  |  | - Analysis of the deficiencies |  | 2nd Q 2005 |  |
|  |  |  | - Proposal for a new system of communication with the aim to improve communication between RI and HQ, individual RI and between the departments of HQ |  | 3rd Q 2005 |  |
|  |  |  | - Communication according to the new system |  | 4th Q 2005 |  |
| New IT system under creation, mainly for records service; training of middle management in communication skills started |  |  |  |  |  |  |
| Objective B.2.5 |  |  | Co-operation and common projects with environmental inspection and enforcement organisations in European countries, the EU IMPEL network and the global INECE network arising from international agreements |  |  |  |
| Done | Started | Not yet started |  |  |  |  |
|  |  |  | - Continuous co-operation with projects, with semestrial evaluation, provided also for the MoE |  | Started in 2003 |  |
| Cooperation with INECE not supported by director |  |  |  |  |  |  |
| Objective B.2.6 |  |  | Adjustment of the strategic plan to a new situation |  |  |  |
| Done | Started | Not yet started |  |  |  |  |
|  |  |  | - Analysis of situation and fulfilment of goals of the strategic plan |  | 3rd Q 2006 |  |
|  |  |  | - Review of the strategic plan |  | Approx. 1st Q 2007 |  |
| Objective B.2.7 |  |  | Increase of effectiveness and transparency of the CEI work through adjustment of activities to the area character |  |  |  |
| Done | Started | Not yetstarted |  |  |  |  |
|  |  |  | - Evaluation of the territorial division reform |  | 3rd Q 2005 |  |
|  |  |  | - Proposal for division of areas for RI and more effective inclusion of the problematic of their areas into their activities |  | 4th Q 2005 |  |
|  |  |  | - Realisation of a new division and more effective inclusion of the territorial problems into practice |  | 1st Q 2006 |  |
| Goal B.3 More effective inspection and enforcement via improvement of used approaches |  |  |  |  |  |  |
| Objective B.3.1 |  |  | Creation and implementation of a unified CEI inspection approach |  |  |  |
| Done | Started | Not yet started |  |  |  |  |
|  |  |  | - Proposal for inspection approach |  | 4th Q 2004 |  |
|  |  |  | - Decision on proposed inspection approach |  | 2nd Q 2005 |  |
|  |  |  | - Full implementation ready |  | 1st Q 2006 |  |
| Proposal was prepared by twinning project |  |  |  |  |  |  |
| Objective B.3. 2 |  |  | Creation and implementation of a unified CEI enforcement approach |  |  |  |
| Done | Started | Not yet started |  |  |  |  |
|  |  |  | - Proposal for enforcement approach |  | 4th Q 2004 |  |
|  |  |  | - Decision on proposed enforcement approach |  | 2nd Q 2005 |  |
|  |  |  | - Full implementation ready |  | 1st Q 2006 |  |
| Proposal was prepared by twinning project |  |  |  |  |  |  |
| Objective B.3. 3 |  |  | Setting up a unified database of subjects with basic data, including their compliance behaviour and inspection results |  |  |  |
| Done | Started | Not yet started |  |  |  |  |
|  |  |  | - Needs and existing databases analysis |  | 4th Q 2004 |  |
|  |  |  | - Testing use of database |  | 1st Q 2005 |  |
|  |  |  | - Database operational |  | since 3rd Q-2005 |  |
| Partial analysis and conception of information system “records service” done before making of strategic plan; Presently tested at RI Prague. |  |  |  |  |  |  |
| Objective B.3. 4 |  |  | Creation of an individual inspection plan for each inspector with the inspection priority for the most significant sources of pollution, resp. most important environmental problems |  |  |  |
| Done | Started | Not yet started |  |  |  |  |
|  |  |  | - Preparation of individual plans |  | 3rd Q 2005 |  |
|  |  |  | - Agreement by heads of departments |  | 3rd Q 2005 and further each 3rd Q of the preceding year |  |
|  |  |  | - Fulfilment of the plan |  | From the 1st Q 2006 |  |
|  |  |  | - Analysis of the fulfilment for the previous period |  | 1st Q 2007 and the each 1st Q of the following year |  |
| Objective B.3. 5 |  |  | Reaching the situation of unified enforcement of the law through development of high-quality methodologies in individual areas of inspection activity |  |  |  |
| Done | Started | Not yet started |  |  |  |  |
|  |  |  | - Analysis of the situation |  | 1st Q 2005 |  |
|  |  |  | - Proposal for setting individual guidelines (methodologies) including setting the priority ones |  | 2nd Q 2005 |  |
|  |  |  | - Development of new methodologies for priority areas |  | 3rd Q 2005 |  |
|  |  |  | - Continuous development of other methodologies |  | By 1st Q 2007 |  |
| Some methodologies (usually media-specific) are in place |  |  |  |  |  |  |
| Objective B.3. 6 |  |  | Meeting the aims of the CEI organisational development by the review of existing and creation of new internal guidelines of the CEI |  |  |  |
| Done | Started | Not yet started |  |  |  |  |
|  |  |  | - Review of the current guidelines |  | 1st Q 2005 |  |
|  |  |  | - Proposal for priorities for creation internal guidelines |  | 2nd Q 2005 |  |
|  |  |  | - Agreement on priorities and creation of new guidelines |  | 2nd Q 2005 |  |
| List of current guidelines prepared |  |  |  |  |  |  |
| Goal B.4 Better motivation of expert staff through Human Resources Management |  |  |  |  |  |  |
| Objective B.4.1 |  |  | Creation of inter related system of staff education, inspired by existing experience and experience in the EU |  |  |  |
| Done | Started | Not yet started |  |  |  |  |
|  |  |  | - Analysis of the situation |  | 1st Q 2005 |  |
|  |  |  | - Proposal of the introductory training with the use of practical experience of the CEI staff |  | 1st Q 2005 |  |
|  |  |  | - Proposal of other expert training |  | 1st Q 2005 |  |
|  |  |  | - Proposal for training for management |  | 1st Q 2005 |  |
|  |  |  | - Proposal of a system for regular sharing of experience from the inspection and administrative activity among individual environmental media |  | 2nd Q 2005 |  |
|  |  |  | - Proposal of the overall interconnected education system |  | 3rd Q 2005 |  |
|  |  |  | - Realisation of the system |  | 1st Q 2006 |  |
| Some general legal rules are in place, but new analysis did not yet take place. |  |  |  |  |  |  |
| Objective B.4.2 |  |  | Positively participate in and support the discussion on the foundation of a training centre for or including inspection and enforcement of environmental law, and possibly for other activities in the area of environment and to contribute to its operation |  |  |  |
| Done | Started | Not yet started |  |  |  |  |
|  |  |  | - Start of supporting the discussion |  | 4th Q 2004 |  |
|  |  |  | - Train trainers (within the Twinning project) |  | 4th Q 2004 |  |
|  |  |  | - Decision about the creation of the training centre (according to the agreement of involved organisations) |  | 1st Q 2005 |  |
|  |  |  | - Develop projects to raise funding of the centre |  | 2nd Q 2005 |  |
|  |  |  | - Ensure training and education activities from the side of the CEI, discussions concerning CEI staff involvement |  | 3rd Q 2005 |  |
|  |  |  | - Involvement of the CEI staff into the education systém within the environmental sector and other organisations |  | 1st Q2006 |  |
|  |  |  | - Start of the operation of the centre |  | 1st Q2006 |  |
| Objective B.4.3 |  |  | Create a strategy for the use of Human Resources Management in the CEI with the objective to achieve better motivation of staff via linking the career development with the educational system, improved personnel policy and staff motivation |  |  |  |
| Done | Started | Not yet started |  |  |  |  |
|  |  |  | - Analysis of the situation |  | 3rd Q 2005 |  |
|  |  |  | - Proposal for a system of career development |  | 2nd Q 2006 |  |
|  |  |  | - Proposal to link educational system and career development |  | 3rd Q 2006 |  |
|  |  |  | - Implementation of the system |  | 1st Q 2007 |  |
| Objective B.4.4 |  |  | Ensure health of the staff and safety of the working place and work system through a safety and health programme |  |  |  |
| Done | Started | Not yet started |  |  |  |  |
|  |  |  | - Analysis of the existing situation |  |  | 1st Q 2005 |
|  |  |  | - Proposal of a consistent programme |  |  | 2nd Q 2005 |
|  |  |  | - Implementation of the programme |  |  | 3rd Q 2005 |
| New analysis not yet started, but certain provisions are in place e.g. on car use, on manipulation with animals during inspections. Health, Safety and Fire protection are regularly assessed (internal control ) |  |  |  |  |  |  |
| Objective B.4.5 |  |  | Reach staff motivation with the aimed rewarding policy, i.e. with the maximal use of limitted sources for the differentiated increase of salary level of staff in relation to their qualification and work demands, also including other motivation means |  |  |  |
| Done | Started | Not yet started |  |  |  |  |
|  |  | ? | - Analysis of the existing situation |  |  | 1st Q 2005 |
|  |  | ? | - Evaluation of the experience and proposal of possible changes |  |  | 2nd Q 2005 |
|  |  | ? | - Full realisation of the new system |  |  | 1st Q 2007 |
| Analysis and evaluation were announced to be done by personnel dept. No documents available for twinning project. Unclear situation. |  |  |  |  |  |  |
| Objective B.4.6 |  |  | Increase of quality and stabilisation of staff by a consistent personnel policy |  |  |  |
| Done | Started | Not yet started |  |  |  |  |
|  |  |  | - Proposal of minimal criteria for recruitment and quality work indicators of individual staff groups | 1st Q 2005 |  |  |
|  |  |  | - Apply individual indicators | 2nd Q 2005 |  |  |
|  |  |  | - Analysis of fluctuation and conditions for staff stabilisation | 4th 2005 |  |  |
|  |  |  | - Proposal for stabilisation programme | 3rd Q 2006 |  |  |
|  |  |  | - Analysis of efficiency of Working Code in the CEI | 3rd Q 2006 |  |  |
|  |  |  | - Proposal for Working Code with clear rules for working behaviour and its realisation in practice | 3rd Q 2005 |  |  |
|  |  |  | - Proposal of common actions to increase awareness of the CEI´s high credit and professional values | 2nd Q 2005 |  |  |
|  |  |  | - Realisation of common activities | 4th Q 2005 |  |  |
| New proposal and indicators not yet developed; there are older from year 2003. |  |  |  |  |  |  |

#### Functional, service goals and objectives

| Goal C.1 Better efficiency of the use of financial resources |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective C.1.1 |  |  |  |  |  |  | Proposal and implementation of indicators of efficiency of the use of financial resources |  |  |  |
| Done |  |  | Started |  | Not yet started |  |  |  |  |  |
|  |  |  |  |  |  |  | - Analysis of the situation |  |  | 1st Q 2005 |
|  |  |  |  |  |  |  | - Proposal of indicators |  |  | 2nd Q 2005 |
|  |  |  |  |  |  |  | - Pilot testing of indicators |  |  | 4th Q 2005 |
|  |  |  |  |  |  |  | - Introduction of monitoring of indicators in the use of financial resources |  |  | 1st Q 2006 |
| Partially started |  |  |  |  |  |  |  |  |  |  |
| Goal C.2 Creation and implementation of the concept of the use of IT in coordination with the information strategy of the Ministry of Environment |  |  |  |  |  |  |  |  |  |  |
| Objective C.2.1 |  |  |  |  |  |  | Building of properly functioning and secured IT in the CEI in relation to the information strategy of the Ministry of the Environment. |  |  |  |
| Done | Started |  |  | Not yet started |  |  |  |  |  |  |
|  |  |  |  |  |  |  | - Analysis of the situation |  |  | 4th Q 2004 |
|  |  |  |  |  |  |  | - Proposal of the conception |  |  | 1st Q 2005 |
|  |  |  |  |  |  |  | - Realisation of the conception |  |  | 2nd Q 2006 |
| Partial analysis and conception was done before draft of strategic plan. Focus mostly on records service. Was not co-ordinated with team that developed the strategic plan. |  |  |  |  |  |  |  |  |  |  |
| Objective C.2.2 |  |  |  |  |  |  | Higher quality of the inspection activity and running of the administration procedures through providing access to information systems of relevant state organisations |  |  |  |
| Done |  | Started |  |  |  | Not yet started |  |  |  |  |
|  |  |  |  |  |  |  | - Analysis of the needs |  |  | 1st Q 2005 |
|  |  |  |  |  |  |  | - Building of functioning internal information system of the CEI |  |  | 2nd Q 2005 |
|  |  |  |  |  |  |  | - Negotiation concerning information exchange between the relevant organisations (into their possible sharing in relation to the stage of relatisation of MoE’s information strategy) |  |  | 2nd Q 2005 |
|  |  |  |  |  |  |  | - Information exchange/eventually information sharing among the relevant state organisations (including access to the Land Register) |  |  | From 3rd Q 2005 |
| Only partial analysis, building of internal IT system without actual coordination with twinning project |  |  |  |  |  |  |  |  |  |  |
| Objective C.2.3 |  |  |  |  |  |  | Increase of the information capacity of the CEI with creation of complex information system connected to data from the whole sector |  |  |  |
| Done |  | Started |  |  |  | Not yet started |  |  |  |  |
|  |  |  |  |  |  |  | - Analysis of the situation (in relation to the project CENIA) |  |  | 2nd Q 2005 |
|  |  |  |  |  |  |  | - Proposal of connection |  |  | 4th Q 2005 |
|  |  |  |  |  |  |  | - Realisation of the system interconnection |  |  | 1st Q 2006 |
| Presently there is a partial connection with the integrated register of pollution (IRZ) |  |  |  |  |  |  |  |  |  |  |
| Objective C.2.4 |  |  |  |  |  |  | Get data more efficiently through connection into unified information system of the state administration |  |  |  |
| Done |  | Started |  |  |  | Not yet started |  |  |  |  |
|  |  |  |  |  |  |  | - Finding out possibilities of connection to individual IS | 1st Q 2006 |  |  |
|  |  |  |  |  |  |  | - Proposal of the connection | 2nd Q 2006 |  |  |
|  |  |  |  |  |  |  | - Realisation of the connection | 3rd Q 2006 |  |  |

In the framework of an EU IMPEL project discussion takes place concerning the establishment of a support centre for inspections of international waste transports. In this discussion several EU countries are involved.