# Benchmark no. 5.2

Minutes Steering Committee meetings

Benchmark prepared by:

Pavel Sřemer (CZ) – OZV CEI Directorship, Prague, BC Project Leader

Rob Bakx (NL) – InfoMil, RTA

Date: 2 June 2005

Minutes of Steering Committee Meetings

During this twinning project a total of 5 Steering Committee meetings was held in the Head office of the Czech Environmental Inspectorate in Prague. One meeting per quarter. The meeting dates were:

- 11 May 2004

- 2 September 2004

- 16 December 2004

- 3 March 2005

- 26 May 2005

This benchmark document contains the minutes of these meetings in the attached annexes. The minutes provide an overview of the participants to the meetings, the discussion that took place and the decisions and actions taken.

ANNEX 1

SC meeting MINUTES

11 May 2004

MINUTES FOR STEERING COMMITTEE No. 1

11 May 2004, 10.00 - 12.00

Attendees: Mr. Pavel Šremer – CEI (PS, Chair), Mr. Rob Bakx – Twinning advisor (RB), Mr. Koen de Kruif – DCMR (KMK, minutes), Mr. Jan Janda – project assistant (JJ), Mr. Ivo Trojan – CEI (IT), Mr. Marek Pur – CEI (MP), Mr. Rudolf Cejnar – Ministry of Environment (RC), Mr. Miroslav Soukup – Police Presidium (MS), Ms. Zdeňka Volná –Ministry of Environment (ZV), Ms. Michaela Horáčková – Ustí nad Labem (MH), Mr. Václav Kubínik – Customs Office (VK), Mr. Jan Kracman – Customs Office (JK), Mr. Daniel Miklós – Fire Brigade (DM), Mr. Václav Vavřička – Fire Brigade (VV), Mr. Mirko Jašurek – Ostrava (MJ), Mr. Jan Prášek – IPPC Agency (JP).

Observers: Ms. Teresa Kozákova – EU delegation (TK)

Not present: CFCU,

1.   Welcome and opening of the meeting

Pavel Šremer welcomed everyone and he shortly introduced himself. He informed the meeting that this was a first Steering Committee and also the kick-off meeting of the project. The kick-off meeting is meant to give an introduction to the project at a practical level to the Steering Committee members and to present the activities as they will be executed during the project.

PS introduced the three main parts of the twinning project: the Strategy development, the Training program and the Informational network. Additionally, there is from the twinning project support in the CEI investment program.

This Steering Committee will be able to discuss all activities as planned now.

Koen de Kruif welcomed on behalf of the Dutch project team partners all members to the committee, explaining that this Committee has an important task to do. It is one of the three management levels of the project.

- The first management level is the project management, consisting of the Resident Twinning Advisor (RTA, Rob Bakx), the project leaders from the Netherlands and the Czech Republic and Jan Janda, (PA, project assistant).

- Second level is the management of the implementation of the project activities, which is managed by the RTA in conference with PS and the Director of the Czech Environmental Inspectorate, Mr. Slanec.

- The third level is the control management, as executed by the Steering Committee.

# The task of this committee is to discuss the progress and the results of the project. It will comment on the planned activities and the draft reports. The comments will be taken into account and used in the further development of the activities. The Committee will receive the quarterly reports. It is expected by the project team that the Committee Members can act on behalf of their respective organisations.

# KMK wishes the Committee a successful project; in that case the project team will experience a successful project as well.

2.   Introduction to all members of the Steering Committee

Mr. Pavel Šremer – SC Chairman / Czech  Project Leader

# Mr. Koen de Kruif – SC Secretary / Dutch  Project Leader

Mr. Mirko Jašurek – Municipality of Ostrava

Ms. Michaela Horáčkova – Municipality of Ustí n. Labem

Mr. Daniel Miklós and Mr. Václav Vavřička – Fire Brigade

Mr. Jan Kračman and Mr. Václav Kubinek on behalf of Ms. Ivana Břicháčkova or Mr. Hynek Kubart – Customs Office

Mr. Miroslav Soukup – Police Presidium

Mr. Marek Pur – Czech Environmental Inspectorate (CIZP)

Mr. Ivo Trojan – Czech Environmental Inspectorate (CIZP)

Ms. Zdeňka Volná – Ministry of the Environment

Mr. Jan Prášek – IPPC Agency

Ms. Tereza Kozákova – EC Delegation (Observer/Advisor)

Mr. Rudolf Cejnar on behalf of Mr. Martin Petrtyl – Ministry of the Environment

Mr. Rob Bakx – Resident Twinning Advisor

Mr. Jan Janda – Project Assistant/Interpreter

Notes to the meeting will be made by KMK. These minutes should be seen as a summary of the presented materials and the comments on it by the Committee. The notes will be sent around to the SC for comments. Please give comments after reading. The improved notes will be approved in the next SC.

3.   Short report on the activities thus far (RTA)

RB reports. Not so much has happened from content point of view. In the beginning quite a lot of attention had to be given to inform stakeholders on the project and to raise enthusiasm at central and regional levels. Much attention had to be given to the administrative procedure. Also attention had to be given to the development of the investment program. The following more specific activities were executed:

3.1 Round tour to regions

Project team and representatives of CEI visited all 10 CEI regions with in total more than 100 persons attending the different sessions, coming from all relevant organisations. The objective was to inform the regions on the planned activities and the expected roles of the organisations present. Some comments of these organisations on the project are summarised below. Not all comments and questions are answered yet, but they will all be taken into account in the further development of the project and written down in the inception report, activity 1c.

- Why not involve courts, since they play a role in enforcements;

- There are ambitions in enforcement activities in other (regional) levels/organisations as well, which may possibly overlap with existing enforcement structures and responsibilities.

- It was noted that there is a lack of clear strategies in enforcement activities

- If there will be developed a Training Center, it may require accreditation. This has to be found out.

- Discussions showed that there is a need for better communication between central and regional level

- We see a need for a good support from the Management to its staff, when regional representatives are involved in activities.

3.2 Connection to 2 other projects.

Until beginning of August, an IPPC project is being executed. This project deals with implementation of IPPC at a practical level. KMK is also project leader of this project. The RTA is from the Environment Agency in the UK. This project has already invited CEI delegates to their training program and PS is represented in the Steering Committee. Good contacts therefore are already existing and useful.

The CENIA project is under German leadership. It deals with monitoring obligations and streamlining existing information. Also here: cooperation where possible and necessary. This has already been agreed.

3.3 Project activities Planning

A planning has been prepared. The planning is being adapted continuously, since the project involvement and their ideas are changing as well. The planning can soon be found on the internet website..

ACTION – RTA organise contacts with other projects; RTA publishes planning on the website.

4.   Strategic plan development (PS, RB)

PS presents some basic elements in the Strategic Plan development. These include: long term planning, a training program, integrated inspection methods, minimum criteria for inspection and involvement of other organisations, partly taking care of connected inspections and enforcement. The Strategic plan development requires the needs of the organisations that are involved in this project. Within the project training and some workshops will be organised to take all the existing strategic plans into account and the combine the relevant strategies. The project will include training on Strategic Planning, where other institutes will be invited too. The project has started with the development of the strategic plan.

RB presents the plans on this activity. In June, two workshops on strategic planning will be organised. These workshops will focus on several main elements of strategic planning. It is a management discussion with management decisions. The Staff will have some involvement in the development of the main strategy.

The workshops should lead to a first draft strategic plan in September, but it may take longer due to important discussions that will come up whenever strategies are discussed. The discussions will include co-operation with all relevant stakeholders in environmental enforcement. When the plan is finished, a start will be made with implementation.

Some comments were given to the introductions.

- Isn’t the strategy in the Law? Will it become a Law? The Law presents the requirements, but mostly not the how of enforcement. So, the strategy will not necessarily become a law! It is the implementation of it. In the project we will involve political level. Also the Environmental Codex will be taken into account. In the end, the Codex may take over part of the strategy. At this moment the project team doubts whether that will take place on short notice. Note: strategy is an ongoing process; it requires up-dates regularly.

- Research institutes and universities are not involved in the set up of the training on strategy development! It has been considered to involve the training institutes of training departments of all the enforcement organisations. All organisations are asked to contact their training staff to involve them in the project.

- Accidents? Crisis management is already executed in an integrated way on the basis of Law 353. There is also connection to the databases of the Interior Ministry. This is useful information for the part on informational networks. The expert dealing with informational networks will take this into account. Further connection with the CENIA project on monitoring will be made. The project CENIA will focus on harmonisation of the most important environmental databases.

Informational networks: In the workshops discussion will take place on which real cooperation activities will be taken up and what is necessary to have good and effective cooperation.

Note Fire brigade: Some cooperation already exists. The CEI should be part of the Crisis Management Team in case of limited but large discharges.

Note Fire brigade:

Law 312/218 Coll. on responsibilities of local self-government officers and Law 218 Coll. on civil servants, both from 2003 limit training responsibilities.  This will influence the set up of a training organisation. The project team will read this paper and involve the relevant persons to prepare the program.

ACTION all

- Provide the project team with existing plans;

- Give your opinion on the existing plans of other organisations that will be sent to you.

- Indicate the strategies that are of interest to you and your organisations. Can you become stronger from the plans

- If there are any relevant institutions, please indicate how to involve them, including their e-mails.

- Laws 312/218 in English to Janda

5.   Training Program Plans

There are three parts to the Training Program: a training center, a training program and a mobile laboratory training program.

5.1 The Training center depends on the availability of centers in other organisations and on the strategy of the institute to develop it.

## 5.2 Training program

The program starts with a Training needs assessment. Existing needs can be send to Janda. An important part of the training program is on the inspection techniques, where experts from the Netherlands will share their experience in integrated permitting and enforcement. In a Train- the- trainer program attention will be paid to skills and to set up of training programs and the execution of these programs. The trained trainers will be involved in the discussions on the tasks also beyond the time of the project. The trained trainers will have tasks in the training centers as well. Mobile laboratory training depends on the investment part of the project and the possible cooperation with Fire brigade on the mobile labs. The supplier of the labs will provide the training. It will all be continued in June.

## ACTION all

- Is there already a training needs assessment? Please give a copy to Janda.

- Are the contacts known to everyone; should there be any names additionally.

6.   Informational networks

Also the work package on informational networks consists of 3 parts: development of monitoring of inspections and accident prevention. The other two are: establishment of a network and development of information exchange.

7.   Program of activities in the second quarter

Ruled by the holiday season

- Workshops strategic planning

- Meet with the regions

- June: input from the partners

- August: training needs

- Discussion training center: June

8.   Dates for future steering committee meetings

The meeting discussed the steering committee schedule. it should be on Wednesday or Thursday. The remaining meetings are scheduled for:

SC2: Thursday 2 September 2004

SC3: Thursday 2 December 2004

SC4: Thursday 3 March 2005

SC5: Thursday 19 May 2005

All of the meetings will be held in the CEI offices in Prague 9.  Each meeting will begin at 10:00 and will finish not later than 12:30.

ACTION all: comment on the proposed dates and days. The dates will be made final in the second Steering Committee!

9. Round of questions

## Laboratory investment?

This investment program is not a part of the twinning. However, the investment will follow the strategy. First strategy decisions have to be taken

Mr. Jasurek: How does the Strategic Plan relate to Codex and laws?

Projects with law making ambitions are sometimes too complex to get results in a limited period of time. That’s why this project focuses on adjustments through management approaches. From practice it is known that a strategic plan can be considered as one of the best tools to make a start with these adjustments.

There was some discussion on the need of cooperation on different topics in environmental enforcement. Clear cooperation is required in case of Trans Frontier Shipments, the implementation of the SEVESO-II directive on large accidents. Etc.

RB mentions the website of the project. Step by step information on the project, but also background information will be available there. The website address is: www.cizp.cz  under the heading “Zahranični vzthay:, further using the menu to the left under ‘Twinning Project’. At present the website is in Czech only, but an English version will be available later.

10. Closing of the meeting

Meeting closed at 12:20.

ANNEX 2

SC meeting MINUTES

2 September 2004

# Version 2004-09-10 (final draft)

# MINUTES of STEERING COMMITTEE No2

# 2 September 2004, 10.00 - 13.00

Attendees: Mr. Pavel Šremer - CIZP, chair (PS), Mr. Rob Bakx – Twinning advisor (RB), Mr. Koen de Kruif – DCMR, minutes (KMK), Mr. Jan Janda - Project assistant (JJ), Ms. Michaela Horackova - Usti nad Labem (MH), Mr. Daniel Miklós – Fire Brigade (DM), Mr. Václav Vávříčká – Fire Brigade (VV), Mr. Miroslav Soukup – Police Presidium (MS), Mr. Mirko Jašurek - City of Ostrava (MJ), Mr. Hynek Orság – City of Ostrava (HO)

Observers: Ms. Teresa Kozáková - EU-Representation (TZ), Mr. Pedro Mauleon - EU-representation (PM), Ms. Zdena Bauerová – Ministry of Finance (ZB), Veronika Hunt Safrankova – EU Department, Ministry of Environment (VS), Ms. Marta Susova - Project assistant (MS)

Not present: Mr. Jan Slanec – Director CEI (JS), Mr. Martin Petrtyl – Ministry of Environment (MP), Ms. Zdenka Volna – Ministry of Environment (ZV)

1.   Welcome and opening of the meeting (PS)

Project Leader from the Czech Republic, Pavel Šremer, opened the Steering Committee meeting. He welcomed the members who could not come for the first meeting and introduced the whole Steering Committee. Project Leader Koen de Kruif from the Netherlands welcomed a new project staff member, Marta Susova. PS informed the committee that a new project co-ordinator from CEI is to be selected, due to change of position of Mr. Ivo Trojan. The name of the co-ordinator will be made public as soon as the final decision has been taken. PS explains the agenda of the meeting.

2. Comments to the minutes of Steering Committee 1 (PS)

Point 3

Q: Were the courts involved? (MS)

A: The courts will be involved in the networking part. They have show their interest in participation

Point 3

Q: Was the website opened? Was the planning put on the web?

A: The website has been opened. The planning is on it via a link on the homepage. For now it is complete in English; work is going on to complete the Czech version. Expected ready in 2 or 3 weeks

Point 3

Q: Were contacts with other projects organized?

A: The contacts with other projects (Phare and IMPEL) were established.

Point 4

Strategic plan development: The project team is pleased with the information on the relevant addresses and possible new contacts.

Point 4

Mentioned law # 353/1999 Col. will set the system of prevention of serious accidents caused by selected dangerous chemical substances and chemical materials. Issues of the crisis management are covered in the law #. 240/2000 Col. about crisis management and changes of some laws.

The English version of Laws 312 and 218 are not available; these laws define the training system, the amount of participants, the type of certificate and accreditation and they determine that all civil servants must have 18 days of training per year. These laws are linked to the plan/law of the State service which is under discussion at this moment. It therefore causes some delays in enforcement of Laws 312/218.

Note of SC: the English version may be available in Usti, where training on these Laws have already started, or in the state archive, since this is an EU obligation.

Q: Did the project team receive any strategic plans? (based on ACTION: Strategic plans to be sent to RTA)

A: Apart from some plans of the MoE there were no plans received. The project team would appreciate still that the Steering Committee members would send their examples of their strategic plans, when available, as soon as possible. If there are no strategic plans, would you please inform the project team about that as well.

#### Point 5

On the training center: The training center development also depends on the availability of centers in other organizations and on the strategy of the Czech Environmental Inspectorate to develop it. The project team would appreciate receiving descriptions of their training centers and existing training needs assessments. The laws 312/218 limit possibilities to set up new training structures.

#### Point 8

Steering Committee (SC) meetings are held between 10.00-12.30h on the following dates:

SC3: Thursday 2 Dec	2004

## SC4: Thursday 3 March 2005

SC5: Thursday 19 May 2005

3.   Short report on the activities thus far (RB)

RB summarized the activities in the second quarter. Reports on all meetings and activities can be downloaded from the website (www.cizp.cz, click “Zahraniční Vztahy”, “click Twinning project”). The main activities were:

- In May a workshop was held for the high level management of the CEI, including introduction to strategic planning and the elaboration of a preliminary SWOT analysis.

- 11 workshops in a round tour to the CEI regional offices (and the head quarters) on the development of the Strategy plan were organized with in total 167 participants. In the workshops the Strategy Program was explained and the Strategy plan development process was started. The workshops delivered a lot of information. The results were processed and presented to the high level management meeting of the CEI on 14 July. The information was received with mixed feelings at this management meeting (see agenda point 4). There was no full will from the management to openly approach the results.

- In total 2 strategic planning trainings were held with 25 participants of all the inspection and enforcement partners. The trainings were evaluated as a success, but some participants were surprised about the CEI participation. CEI had sent quite some lower (and non-) management level to the meetings.

- Another 2 strategic planning trainings were held for the middle management of the CEI with 45 participants focusing on the development of the inspection and enforcement approach, as important part of the overall strategy. These workshops had a very good evaluation, with average ‘very good’. Exception: the evaluation showed only ‘sufficient’ on the question whether the training was useful in their present work

- There was a workshop on informational networks about possibilities to intensify co-operation between enforcement partners. In this meeting, good discussions identified points for further co-operation.

- The first thematic workshop on the development of the training center was delayed, to fit in better in the timetable. It is now planned end of September.

- First draft minimum criteria report finished. To be fine tuned.

- The Benchmarks of quarter 1: all benchmarks are ready, but not everything has been written down on paper. With the new assistant aboard all will be published as soon as possible.

# Q: What were the results of the round tour?

There is a rather common view between management and other staff members on the CEI role and tasks, including the priorities. This includes the inspection and enforcement approach. The formal development of the inspection and enforcement approach is needed, since many inspectors in practice still use their own approach, which is not good for a professional organization. It was observed that there is a difference between perceived and preferred management style. There are many motivators for the work important. Salary is important but not number one; how to work with colleagues is perceived more important. A full overview of the round tour results can be found on the project website (www.cizp.cz, click “Zahraniční Vztahy”, “click Twinning project”, click “Work packages”, Scroll to Work Package 2, paragraph 2a, click “Participatory workshops”) .

4.   Strategic plan development (PS)

### The most important point of the agenda is the development of the Strategic Plan, Work Package 2. There is not sufficient development. It has to be noted that the consequence of having no strategic plan means that the investment component of the project is endangered. PS introduced the activities under this work package. There was a series of workshops, with the management and the middle management in separate sessions.

### Unfortunately the process of developing a strategy was not supported by the Director of  the CIZP. PS would like to apologize for the fact that too low level of management was sent to the strategy training, because of this lack of support.

In the last 2 strategy trainings the middle management of  CEI was much more involved in these workshops dealing with inspection and enforcement approaches. BUT: support of the top management is required before the discussions on the development of the strategy can be continued.

The delay in the development of the strategic plan effects the time management of the project. There are some activities and results delayed.  It  can be foreseen that under unchanged circumstances at least the benchmarks 2.4 and 2.5 will not be achieved. This also effects the investments. The EU-representation was very clear in this respect: when there is no strategic plan, there can be no investment plan, and therefore no investment at € 1.4 million (EU money) to the Czech Republic. The Twinning Advisor has to approve whether the investment plan fits in the Strategic plan.

Some specific remarks are:

- The CEI management has discussed investment topics with MoE and CFA, without notification to the RTA. This does not promote transparency in the investment strategy. (VS).

- The Twinning Covenant was approved by the DEC and is binding. Therefore the planned activities should be followed. As for the investment part from Phare, it should be in line with the project fiche.) If the benchmarks given in this document are not achieved there is the danger that the CR can loose the funds allocated for the investment part of the project. (1,4 Million €). (VS and TK)

- The existing communication between Twinning Advisor and TK shows that the project team makes maximum effort to solve the problem. The initiatives should now come from the CEI management. As for the investment, if investment needs are not clarified and equipment not tendered on time, financial allocation worth € 1.4 million (+ CZ co-financing) will be lost. (TK) It must be clear that the Investments are closely linked to the strategic plan. The Twinning Advisor has the responsibility to approve the investment plan (PM).

Q: Co-financing reserved?

VS: According to the information from the Department of Integrated Financing, the co-financing part was allocated in the budget of MoE by the Department of Budget.  On 28 July the last version of specifications of the co-financing part (investiční záměr) was sent by economic division of ČIŽP to the Budget Department (MoE) in copy to the Department of Integrated Financing (MoE).The Department of Budget requests  some adjustments in the technical and formal details. The technical specifications of the investment part from Phare were sent by CIZP to Department of Integrated Financing (MoE) in April 2004. New version is expected depending on the twinning part (Strategic plan activities). The twinning partners and the Steering Committee members expect the decision of the CEI Management – to make the Strategic Plan as soon as possible.

The project team welcomes all support to prevent further misunderstandings between the project team and the CEI management. Also, the new Codex influences the content of the Strategic plan. It includes even some changes in structure of the enforcement institutions, which need a clear strategy to be able to cope with. The Codex therefore strongly promotes a quick further development of the strategic plan..

Steering Committee conclusion: It is strongly recommended by the Steering Committee that the Management of CEI starts supporting the development of the Strategic plan.  Otherwise, the sources at 1,4 Million € can be lost.

5.   Training Program (RB)

The training needs assessment will be performed with a tour to the regions. The result will be used to detail the content of the training program to the inspectors. The training program will be offered as one of the possible training programs within the context of a training center.

The Training center has been shifted backwards because of time problems caused by discussions on strategic plan and investment. In this way however the comments on new law (312/218) can be included. The health institutes are happy with the training program, since it will make the co-operation between the environmental inspectorates and the health inspectorates more effective.

The Training program will start in September with a Train-the-Trainers training. This first training will prepare the future trainers to be a trainer. The trained-trainers will later get a training on-the-job, when they will have to deliver a part of the training within the inspectors training program.

6.   Informational networks (RB)

A high level meeting was organized on 10 August. This meeting defined the needs and the feeling for a network. The main needs were:

- Information exchange

- Need for co-operation

First now is to go back to the regions. They have to use the informational networks.

A workshop on 1 September focused on the information exchange inventory between all the inspection institutions. The result will be published on the web.

7.   Program of activities in the third quarter (RB)

- A tour to the regions on the training needs

- Two times a train-the –trainer training

- Further work on the informational network

- High level management workshop on further development of the network, to take care that the network will develop also beyond the time frame of the project

- If the strategy plan develops into something useful and effective, we than inform the regions on the expected effect for regions in a tour

8.   Round of questions (PS)

Q : How far is the plan? (TK)

The Strategy plan has a foundation. The raw materials for the Inspection and enforcement approach have been developed. We will have to reflect on the new Codex as well. It is presently shooting at a moving target. The advantage is that we are also influencing the direction of the target.

Q : What will be in the Strategic plan?

PS: The CIZP is a young institute that needs directions for the future beyond 1 year. It contains the actions on short and longer term. It also will have to lead to a changed WORKING culture at the institute towards an integrated approach. The needed change of direction should be supported fully by all management levels.

Q : What is the time schedule now? (TK)

First we will have to continue the Strategic Plan development, so that we will be able to finish the important benchmark 2.4. After that, it may be best to discuss as project team with the EU-representation to prioritize the other activities. The decision on the prioritization will have to be taken by the SC in December. Members of the Steering Committee agreed that action has to be taken as soon as possible, preferably already this month.

9. Closing of the Meeting

The meeting was closed at 12:45h. The chairman thanked everyone for the co-operation and support.

ANNEX 3

SC meeting MINUTES

16 December 2004

# MINUTES of STEERING COMMITTEE No.3

# 16 December 2004, 10.00 - 13.00

Attendees: Mr. Pavel Šremer - CIZP, chair (PS), Mr. Rob Bakx – Twinning advisor (RB), Mr. Koen de Kruif – DCMR, minutes (KMK), Mr. Jan Janda - Project assistant (JJ), Mr. Martin Petrtyl – Ministry of Environment (MP), Ms. Zdenka Volná – Ministry of Environment (ZV) , Mr. Daniel Miklóš – Fire Brigade (DM), Mr. Václav Vavřička– Fire Brigade (VV), Mr. Mirko Jašurek - City of Ostrava (MJ), Ms. Ivana Břicháčková – Customs Office (IBR), Olga Klášterková – ČIŽP (OK)

Observers: Ms. Zdena Bauerová – Ministry of Finance (ZB), Veronika Hunt Šafránkova – EU Department, Ministry of Environment (VS), Mr. Arnošt Cetkovsky – CFCU (AC), Ms. Alena Hrbková – ČIŽP (AH), Ms. Ivana Biková – IPPC Agency (IB)

Not present: Mr. Jan Slanec – Director CEI (JS), Ms. Michaela Horáčkova - Usti nad Labem (MH), Mr. Miroslav Soukup – Police Presidium (MS), Mr. Hynek Orság – City of Ostrava (HO), Ms. Teresa Kozáková - EU-Representation (TZ), Mr. Pedro Mauleon - EU-representation (PM), Mr. Marek Pur – ČIŽP (MP), Mr. Jan Prášek – IPPC Agency (JP)

1.   Welcome and opening

Olga Klasterkova’s membership of the Committee was 'endorsed' by the Steering Committee. She will have a role in the development of the activities on the training centre and coordination of activities with the ČIŽP, together with the RTA.

The Chairman thanks the Steering Committee, since they contributed concretely to the project progress after the last meeting. The assisting Member States Project Leader, Koen de Kruif, informed the Committee that the project account is now under responsibility of the Centre for Foreign Assistance at the Ministry of Finance. He wished them good luck with the project team. Competences are taken fully. The Quarterly Report from now on will be sent to CFA, and also to the Central Financing and Contracting Unit of the Ministry of Finance.

2.   Minutes Steering Committee2

No comments to the minutes

Decisions:

- Quarterly Reports 1 - 3 will be sent to participants of the Steering Committee

- The content of the Quarterly 3 Report will for the larger part be discussed during this meeting

- Minutes Steering Committee 2 were approved

- 3.   Strategic plan development

- Many workshops were carried out in the area of strategic planning. The process of finalisation of the strategic plan had stagnated due to insufficient support  by the ČIŽP  management . Support of the Steering Committee after the last meeting had led to further developments but not to signing of the plan as yet. This would mean no direct use of the investment budget, since this required a signature of the RTA, after checking its alignment with the finally approved Strategic Plan. Concerns were raised from the political level in the Netherlands (the Dutch minister and the DCMR director), the Czech EC representation and the Ministry of Finance. In discussions between the Ministry of Environment and ČIŽP  the plan was approved and signed on 1 December 2005. This plan will be circulated to all SC-members. Comments are welcomed.

- It should be noted that the prolonged discussion has led to delays, also in other project activities.

- The Project Fiche had to be adapted, since several investment options were changed due to final outcome of the strategy discussions. The deadline for handing in the investment needs was not achieved, but one day too late. It will now be assessed this week by the MoF/MoE. A division in an EU and a Czech financial part has  taken place. In the tender adjustments may  be made to align with the rules for open competition. For now, it is not a problem for the needs analysis.

- Decision:

- The final version of the Strategic Plan will be sent to the Steering Committee participants

- Further approval at the level of the ministry on the strategic plan does not seem to be necessary, after it was signed by mr. Slanec.  It was initially scheduled to have a meeting on the strategic plan at the level of the Minister  (Minister, mr. Miko, mr. Novotny, mr. Bakx, mr. Slanec). According to Mrs. Hunt the meeting does not need to take place at Minister level when they are no problems.

- 4.   Training program and training centre

# Training programme

- A training needs assessment was carried out. A specialist training programme has been executed to train trainers  with 8 representatives of ČIŽP  and 6 from other institutions). It consisted of two training weeks and 2 seminars designing a 3 week training programme on inspection and enforcement techniques. The weeks l and 2 will be held in a training centre outside Prague. The third week will focus on specific expert topics. The trained trainers will participate as trainers. There is one problem at this moment: there seem to be insufficient financial resources to have a full participation in an external training centre. A new proposal will be prepared by the Project Team, and send to the ČIŽP director within one week.

- Training centre

- In total, two meetings were held with inspection and other institutes on the establishment of a training centre for environmental inspectors. The conclusions were:

- No institute wants a new building;

- There is a very strong interest in cooperation;

- A team of representatives from the Ministry of Environment, the Czech Ecological Institute (the IPPC agency) and the ČIŽP will work out a concept  for a training centre and discuss this with the twinning project team .

- The financing options will be discussed later.

# Questions (PT=project team, PS= Pavel Sremer)

- SC: what does establishment mean for this project .. ?

- PT: The establishment includes an agreement between all the parties on the responsibilities of the centre with a list of the tasks that have to be executed to run the centre. It also includes the financial and human resource management, and the required expertise that is necessary to execute the tasks.

- PS : from project budget on investment maybe some funds used for extra time input to establish the centre. This discussion has to involve the MoE-Budgetary department

- SC : Was there no need before? And is there no training today?

- PS : There is a training, but this is not an integrated system of training. The new centre is intended to include also the requirements of the Minimum criteria for inspection.

- SC : Is there an option to broaden the centre to the needs of the MoE?

- PT : It was thought to be better to have concrete results first (on specialists topics) and then continue with copying skills to other institutions with proof of success.

- Conclusions:

- Focus will be on integrated system of training, not for buildings

- 5.   Informational networks

- The ideas on the use of networks existing at the management level were communicated to workshops in the regions. The workshop inputs were brought back to the central management level. The focus of the network (its topics) was concluded upon. Now the discussion takes place on the best structure for the network. Three practical pilots in network cooperation will be carried out, supported by the management meeting of the network.  These 3 pilots are: hospital waste; car wrecks; and Transfrontier Shipment of Waste. The management meeting established a small Network Working Group (NWG) of 3 persons to work out a proposal for the network structure. The NWG members are Jitka Jenšovská (ČIŽP), Jiří Jungr (Ministry of Agriculture) and Ivana Hrušová (City of Prague).  The  first pilot workshop was on car wrecks, held in Prague in November. Possibilities to take action were identified as well as practical problems that call for a solution. Further meetings will have to lead to a plan of action. The  follow-up meeting on car wrecks still has to  be planned by the ČIŽP. This will no longer be under the  responsibility (but where possible however with the support) of the twinning project. Mr Slanec has informed the Project Team that he is satisfied with the input in the ČIŽP network activities.

- No further comments.

- 6.   Programme of activities 4th project quarter

- The training programme will be executed according planning in January and March 2005

- A study tour will take place in the Netherlands for 6 persons (programme and report will be sent to the Steering Committee

- Extra project time will be asked for at the CFA [note: not allowed; it is not possible due to twinning regulations].

- Otherwise: other financial and legal possibilities have to be found. If not, it will lead to  changes in the results.

- Decision:

- Study tour program and report will be sent to participants of the Steering Committee

- 7.   Round of questions

- SC /Bauerova: explicitly expressed that she expected that all relevant meetings in investments should take place in the presence of the RTA and the Czech project leader. She referred here to a meeting at the Ministry of the Environment last Monday. Mr. Petrtyl explained that he is to blame for that. He will take this into account in future meetings. This particular meeting was an ad hoc meeting on provisional division between EU and MoE funds.

8.   Closing of meeting at 12:00 h

ANNEX 4

SC meeting MINUTES

3 March 2005

Integrated and Planned Enforcement of

Environmental Law

Phare Twinning Project CZ03/IB/EN/01

The Ministry for the Environment (Czech Republic)

The Czech Environmental Inspectorate,

DCMR Environmental Protection Agency

InfoMil - Information Centre for environmental licensing and enforcement

4 March 2005

## MINUTES STEERING COMMITTEE (SC) No. 4

## 3 March 2005, 10:00 – 12:00 h

Attendees: Mr. Pavel Šremer - ČIŽP, chair, Mr. Rob Bakx – Twinning advisor, Mr. Koen de Kruif – DCMR, minutes, Mr. Jan Janda - Project assistant, Mr. Martin Petrtyl – Ministry of Environment, Ms. Zdenka Volná – Ministry of Environment, Mr. Václav Vavřička– Fire Brigade, Mr. Hynek Orság – Moravsko-Slezský Regional Office, Mr. Miroslav Soukup – Police Presidium, Ms Eliska Chomatova, new project assistant,

Observers: Ms. Zdena Bauerová – Ministry of Finance, Ms. Alena Hrbková – ČIŽP replacing mr. Slanec, Ms. Ivana Biková – IPPC Agency, Mr. Holec, EU Department, Ministry of Environment, Mr. Klapuš, deputy Director ČIŽP replacing mr. Slanec

Mr. Arnošt Cetkovsky – CFCU, (after the meeting)

Not present: Mr. Jan Slanec – Director CEI, Ms. Michaela Horáčkova - Usti nad Labem, Mr. Marek Pur – ČIŽP, Mr. Jan Prášek – IPPC Agency, Mr. Daniel Miklóš – Fire Brigade, Mr. Mirko Jašurek - City of Ostrava, Ms. Ivana Břicháčková – Customs Office, Olga Klášterková – ČIŽP, Ms.Veronika Hunt Šafránkova – EU Department, Ministry of Environment

### Welcome and opening of the meeting (PL-BC)

Mr. Sremer opened the meeting. It was observed that Mr. Slanec was not present in the meeting, although this was written as a recommendation in the interim-monitoring report. He was represented by ms. Hrbkova and later by mr. Klapuš. Ms Chomatova was welcomed as new project team member. Mr. Holec replaced Ms Hunt Šafránkova.

- Minutes of Steering Committee 3 (PL-BC)

The minutes were received by all. There were a few comments:

- The study tour report has almost been finished. It will be sent out on short notice.

- The project team requested extra project time. This appeared not to be possible due to lack of financial resources within the project budget. As extra time needs extra funding for a.o. time of the RTA an available budget is essential according to the rules of the Centre for Foreign Assistance. However, a shift of surplus of budget from investment part to twinning part is not possible in this phase of the project. Hence: the project will finish at 7 June 2005.

- The investment plans will be explained under heading 3.

- The minutes were approved.

### Developments in the Third Quarter / Strategic Plan development (PL-BC)

The third quarterly report has been written and has been sent to the Centre for Foreign Assistance. The ČIŽP director has commented on this report and reactions to the comments have been written by the Czech project leader. Mrs Bauerova was pleased that the majority of the participants was satisfied with the training programme. She was concerned about the letter that the CIZP director had sent to her, but that this letter is not fully covering the real situation. Since Mr Slanec is not here, he cannot react. Therefore, Mrs Bauerova will organise a meeting with him, the RTA, Czech project leader and representatives of the Ministry of Environment. She would like to remind the committee that every authority themselves is responsible of solving their own internal problems. In this case it is the responsibility of the Ministry of Environment. Mrs Bauerova also received a second letter from Mr. Slanec, after she asked further explanation on the first. This letter will be discussed in the meeting with her. She will sent a translated version of this  second letter to all involved parties.

The project has also been evaluated by external consultants. This report has been discussed and approved on 1st March  at the Ministry of Finance, chaired by Mrs. Hendrichova from the MoF. This report included an evaluation as often performed according to international standards.The evaluation found problems in effectiveness, efficiency and sustainability of the project results, caused by insufficient support from the ČIŽP management. It supported the findings that the top-management should improve their commitment to the project, to be shown a.o. by the presence of the Director or his replacement at steering committees. This conclusion of the report was supported by representatives of ČIŽP, as asked by the chair of the evaluation commission. The next report will be written in a years time. Mr. Petrtyl will take care that project leaders will be invited in the kick-off meeting next year.

The Strategic plan was completed and signed by Director Slanec. The Strategic plan has lead to adaptations in the investment plan. Therefore, the investment component of the project had to be changed, including the original project fiche. Nature protection was not a part of the project fiche anymore since this was agreed in the project covenant and confirmed in the first revision of the project fiche. Activities were executed for the CIZP network and the Training and Methodological Centre (TMC), as was approved in the Strategic Plan. The CIZP staff commented on the Strategic Plan, and suggested prioritisation of different items. These priorities were presented to the Chief Inspectors meeting as point of view of inspectors.

The study tour to the Netherlands was held in the second week of January 2005. The tour focused on management issues. The evaluation showed that all participants were happy with the organisation of the tour, the time that was put in the organisation, and the atmosphere they encountered in the different organisations. They saw an agency with similar size and operational functions in a region with high concentration of industry and a high need for safety and emergency response. They now saw that co-operation with many other organisations was required for good operation. All questions were answered (including the cooperation mechanism between  the Dutch environment agencies and the water boards who are responsible for water issues.) and lessons were learned in co-operation issues and in communication with the public. They understood the value of improving contacts with companies. An organisation like InfoMil is clearly missing in the Czech Republic, to serve different authorities with information on interpretation of law and guidelines.

### Training program and training center (RTA)

###### Train-the-Trainer programme (November 2004)

A train-the-trainers programme has been executed in Quarter 3. These trained trainers were used in the training programme on technical issues in Quarter 4. The Czech trainers prepared and executed part of the training and received feedback to their performances. The second technical training programme will complete the Czech trainers’ programme. These trainers will receive trainer-certificates in the final conference in May/June 2005.

Technical Training programme (January 2005)

The 8 Czech trainers and 5 Dutch trainers together prepared and executed for 40 inspectors a programme on integrated inspection. Most participants were very enthusiastic; some did not recognise themselves in the activities. Average evaluation score is 7.5-8 (on a Scale up to 10). One striking element in the evaluation: relevance for own work scored 6.8. Apparantly some activities were not in line with the expectations on the training, despite the efforts of project team and trainers to cover all elements that were mentioned in the training needs assessment. It reflects the fact that ČIŽP inspectors do media oriented inspection and therefore do not see integrated approaches as important for their work. Some logistical problems occurred with the trainers. Some of them did not complete all the tasks that they had promised before.

The Training programmes 2 and 3 will be executed by Czech and Dutch trainers too. The training programme will focus on:

1. Social Skills (time management, communication and negotiation techniques, EU minimum criteria for environmental inspections)

2. Four separate topics as stated in the project fiche (GMOs, Seveso-II, Water Framework directive, Transfrontier Shipments of Waste)

For quick and adequate transfer of expertise, the project team had asked head of expert departments of the ČIŽP  for specific questions. The questions will be processed during the training.

Training and methodological Centre (TMC)

A discussion has taken place between ČIŽP and the Czech Ecological Institute (CEU). If it will be decided to establish a training centre, it will be housed in the CEU. The project team is very happy with this progress. Further action is required. Bikova would like to see the official result of the discussion. A follow up is planned on the TMC by a Dutch Czech bilateral project on training centres. Other results from twinning projects or bilateral project will add to this project. The TMC will use trained trainers, also from this project.

Conclusion. The TMC is on the list of activities of the ČIŽP and CEU. It has been agreed that a future ČIŽP training programme will make use of the training centre.

5.   Informational networks (RTA)

Three bigger meetings on information networks have been executed and also two thematic network meetings. These thematic meetings were used to show the use of network meetings. There is no legal obligation to organise these meetings, but there is also no problem to do it. Every network meeting will have to conclude with follow-ups.

The first theme was organised in Prague on inspection of Car Wrecks. The conclusion of this meeting was that a working group of ČIŽP, City of Prague and the Ministry of Agriculture will develop a Czech network structure in which legal problems in combined inspections will be discussed.

The second theme has focused on preparation of waste permits. This second theme came up as topic during a round tour to the regions. All thematic meetings were well received, but do need follow-ups and support by the management to have lasting effects. The effect is better discussion on different inspection approaches and interpretation of laws. An important outcome of the second meeting was that it would be beneficial to the regional authorities to allow the regional inspectorates to play a role in the waste permit. This will improve enforceability and lead to better permits with better environmental results. Negotiation between regional environmental and health authorities and regional environmental inspectorates should define the future involvement of inspectors in permit making.

The third meeting was planned on co-operation in law 353 on Seveso-II but due to time and organisational constraints this will not be possible. The main topics of this network meeting will be dealt with in the third training.

Networking document

The project team has noticed that the management of ČIŽP is working on the document of Networking. The project team would like to make even further progress and is willing to support the further development of the networking document.

- Programme of activities in the fifth quarter (RTA)

In March, the second and third technical training programmes will be executed. The programmes are ready. The invited participants for the 2nd programme are the same as in the first programme. The participants who will have attended the two training programmes and who completed 2 self-evaluations will get a certificate.

In April, a feedback on the results of all project activities will be provided to the regions. There will also be an information exchange by means of workshop or interview with key figures. The connections to the CENIA project on information exchange will be defined.

May/June will have the closing workshop and the final reporting and benchmark reporting. The closing workshop was originally planned in the week of 17-19 May, but will be rescheduled on short notice, since the ČIŽP management will be absent that week. Rescheduled dates will be communicated to all Steering Committee members on short notice.

### Round of questions (PL-BC)

Investments

There is a new and last final version of the investment plan that has to go to Mr. Cetkovsky this very week. A new Project Fiche has been written to allow for the new investment plan. This fiche is ready, and given for approval to the Ministry of Environment and for final approval to CFA of the Ministry of Finance.. Mrs Bauerova informs the meeting that the RTA will sign the needs analysis as an independent expert.

Recommendations of the monitoring report

One of the recommendations of the monitoring report was that the Director of CIZP would have to be present in the Steering Committee meetings. However, in this meeting he has sent his deputy Mr Klapus. Mr. Klapus informed the meeting that the Director of ČIŽP is at the Ministerial Management meeting. The RTA informed Mr. Klapus that the project team would welcome a proposal for a different day and time, but that staying out without giving notice is not the way to do it. The project leader from the Netherlands is also expected to be at the meeting and he cannot easily change his flying dates. For the last Steering Committee meeting a date will be set together with the secretary of the Director.

### Closing of the meeting (PL-BC)

The meeting was closed at 12.06. The chairman thanks all for their presence. He would like to invite all steering committee members and observers to the final conference and the steering committee that will be connected to the conference. The original planned dates were 17-19 May. Due to other international obligations of the ČIŽP management, it is proposed to change the dates to 24-26 May (still to be confirmed).

ANNEX 5

SC meeting MINUTES

26 May 2005

Integrated and Planned Enforcement of

Environmental Law

Phare Twinning Project CZ03/IB/EN/01

The Ministry for the Environment (Czech Republic)

The Czech Environmental Inspectorate,

DCMR Environmental Protection Agency

InfoMil - Information Centre for environmental licensing and enforcement

27 May 2005

## MINUTES STEERING COMMITTEE (SC) No. 5

## 26 May 2005, 10:00 – 12:00 h

Attendees: Mr. Pavel Šremer - ČIŽP, chair (PL-BC), Mr. Rob Bakx – Twinning advisor (RTA), Mr. Koen de Kruif – DCMR(PL-MS), minutes, Mr. Jan Janda - Project assistant, Mr. Martin Petrtyl – Ministry of Environment, Ms. Zdenka Volná – Ministry of Environment, Mr. Hynek Orság – Moravsko-Slezský Regional Office, Mrs Lucie Vravnikova CENIA, Mr. Jan Slanec – Director CEI, Mr. Martin Vykouk, Ustí nad Labem city  replacing Mrs. Michaela Horáčková.

Observers: Ms. Zdena Bauerová – Ministry of Finance, Mr. Holec, EU Department, Ministry of Environment, replacing Mrs Hunt, Mr. Arnošt Cetkovsky – CFCU

Not present: Ms. Michaela Horáčkova - Usti nad Labem, Mr. Marek Pur – ČIŽP, Mr. Jan Prášek – IPPC Agency, Mr. Daniel Miklóš – Fire Brigade, Mr. Mirko Jašurek - City of Ostrava, Ms. Ivana Břicháčková – Customs Office, Ms.Veronika Hunt Šafránkova – EU Department, Ministry of Environment, Mr. Václav Vavřička– Fire Brigade, Mr. Miroslav Soukup – Police Presidium

1.	Welcome and opening of the meeting (PL-BC)

Mr. Šremer opened the meeting. The agenda was approved. Mr Slanec arrives later and expresses his surprise that the meeting was planned on a Thursday, which is not a covenient day for him due to other obligations.

(Note: this meeting was replaced to this week and day, due to the planned absence of  Slanec. He expected participation in an OECD meeting.)

- Minutes of Steering Committee 4 (PL-BC)

The minutes were received by all. There were a few comments:

- Study tour report under 3 was sent around only yesterday, with apologies. It is available in hard copy at this meeting

- A meeting that was promised under 3, to be organised by mrs. Bauerova, did not take place. The state of the project was discussed in the monitoring meeting on 1 March 2005. There were and will be different other opportunies for the ČIŽP management to discuss with the Ministry of Finance the standing issues.

- The conclusion drawn under informational networks on car wrecks was not drawn by the thematic meeting on car wrecks but by the management network meeting.

- The minutes were approved.

Quarter 4 report was completed and approved. No formal remarks (in English) were delivered to the project team. A letter was written by the ČIŽP management and sent to different members of the Steering Committee, to the Ministry of Environment and the Ministry of Finance. The main issue in these letters is the incomplete fulfilment of the requirements of the IPPC legislation according to the project team’s Quarter 4 report. A fierce discussion develops.

In the following the minute maker  tried to give an extensive report on this discussion that took place, since it is essential for the understanding of the discussion now and the recommendations in the final report later.

The Ministry has received a report on implementation on IPPC by ČIŽP. This report says that ČIŽP fulfils from Czech law point of view the IPPC directive. ČIŽP activities in IPPC implementaton have been assessed by the project team. Two main issues became clear:

- The EU directive does allow also for other enforcement instruments than presently allowed in Czech law;

- ČIŽP does not have a full scale  integrated approach in inspections.

According to Slanec it is not possible to have the expertise within the ČIŽP from an integrated perspective, since the scope of knowledge on media approaches does not make this possible. ČIŽP does not have the obligation to do integrated inspections, since this is a task of the regions. However, ČIŽP is trying to strive for integrated appraoches. Current permits are very demanding in relation to the qualification of the inspector and therefore media experts are involved. Transformation of media experts into IPPC experts takes time. Bakx: ČIŽP can already do it, also under present law. It is not a legal issue,but a managerial one. The regions show strong progress in integrated approaches. Slanec: it depends on the permits. The permit is the responsibility of the regional authority; ČIŽP only controls the permit conditions. ČIŽP can improve it, but the ministry does not share the philosophy that an inspectorate can be involved in the permitting process. This is a difference between Dutch and Czech law. Bakx: it is not difference between Dutch and Czech approaches. We talk about an overall EU approach. If the Czech Inspectorate can not do it, it may raise the question whether the Czech Republic has implemented the directive in the way it was intended.

Šremer received a letter from Slanec to restrain ourselves from informing the EU on this incomplete implementation, because it will influcence badly the image of ČIŽP. However, this is an EU project and it has to provide information to EU levels. How is it possible to the project team not to do it? This information will not have a bad influence on the image of the ČIŽP. It shows that the administrative system as a whole is not completely at the required level. De Kruif: we are not here to destroy the image of ČIŽP, but to assist ČIŽP in implementation of the EU requirements. It is the responsibility of the Czech government to do it properly. It is now our right and responsibility to report about the results of the project to the European Commission.

Slanec: It has been reported that the organisational procedure of ČIŽP does not allow integrated controls. But if ČIŽP does not fulfil its obligations set by the law on IPPC, he would have to resign.  Bakx: At this moment ČIŽP is not an integrated organisation. It is not to blame anyone, but it is an observation and a challenge to do something about it. Šremer: it is not sure that it is question of a law. We have media laws and integrated prevention law. Through a painful procedure we can integrate the media laws into integrated, and that will take more than a few years. It is a pity that ČIŽP did not use the project to speed up the process. Slanec: does not accept anything that says that integrated approach is possible without legislative changes. He finds the twinning team pushing in this respect. The ČIŽP is paying a fine for breach of the law on the protection of personal data and all the information concerned minimum criteria and publication of information. Šremer: the project team does not think that it is a fault on organisation of the work, but that there is insufficient attitude now to want to take the initiative to change. Orsag: The inspectorate Ostrava is following the regional level. At this moment it is a problem to use the current media specific legislation. It is not an optimal situation to use it for an integrated approach. In Ostrava region they have most IPPC-installations of the Czech Republic. He agrees with Slanec that a law change is necessary to make it easier to involve staff of ČIŽP, but it is not impossible. They are already cooperating with the ČIŽP in permitting. We do need, however, permitters with specialised tasks in different fields. E.g. to have permitters/inspectors in agriculture, or the chemical sector or others. Next to that, inspectorates can also have a consultative role in permitting and investments. Now we should not forget that most of the structures at present are medium oriented and it takes years to change.

Discussion: what is the legal situation and what can you do beyond legislation through management. Integrated approaches is about using best practices and not about doing everything. It is about organising information flows on the different activities, about organising the work, with contacts with specialists and in effective planning of the work and priorities in inspection.

In this meeting, it was not possible to get to an agreement between mr. Slanec and the project team. Further discussion does not make sense at this moment. Petrtyl: we now know each other’s opinions. Mr. Slanec opinion will be used too. The legislative framework must be changed to allow better integrated approaches. Possibly the organisations will already be able to adapt earlier into a proposed direction of the recommendation. He asks the project team to make a calculation what is the required number of inspectors to cope with the number of integrated permits as it is done in other member states. Bakx: we can certainly say something on the need for the number of inspectors with the right level of qualification. It will however take time to make this calculation and will depend on the prioritisation and planning mechanisms, as well as inspection frequencies to be used. This way of calculating also provides a defence mechanisms against budget cuts, since a budget cut will than also limit the amount of inspections, and consequently may be harmful to the environment. Slanec: new additions in the law have lead to more requirements in inspections (a.o. Natura2000) and still we have budget cuts. It is working differently here. Bakx: it is impossible to sit still, we have to use the budget to do the most and optimal. Not adapting to the new situations will finally lead to the death of the organisation. When you have ideas how to cope with the new situation you have to be strong and challenging in it and make use of the chances. He advises not to be too defensive.

Other remarks:

Bauerova: In summary, according to Dir. Slanec in the framework of the current legislation it is not possible to ensure integrated approaches in inspection work. Meanwhile, the twinning team states that in the framework of current legislation it is possible to ensure a shift towards enforcement of EU law.

Orsag: In every region there is a shortage of staff. There are 4 IPPC permit writers in Ostrava, and some more media experts. The media experts are involved in the permitting process and also do other types of work. From here it should be developed.

Cetkovsky: There is still a different point of view. Are you willing to add the difference in opinion in the report.

Decision: in the final report the project team will give the recommendations they think are necessary to make. The director of ČIŽP will be offered space to react to the general recommendations, provided that they will be offered to the project team in English, before the end of the project on 7 June 2005. It will be taken up as an annex unchanged.

### 3.    Strategic Plan development (PL-BC)

The plan was approved by the management and implementation followed the approved. Now an implementation table is produced by the project staff for benchmark 2.5. No further written material was yet provided on the activities that were executed. The implementation table will be produced on short notice, with state of implementation and proposed deadlines.

One of the important benchmarks that has been produced in the past quarter was on minimum criteria.

Slanec would like to discuss the paper work before it leaves the house. Šremer says that there is always the project team’s view and the opinion of the ČIŽP on it. We have to find ways how we use the ČIŽP information in the table on minimum criteria.

Decision: The benchmark on the implementation of the strategic plan is almost ready. The table summarising the results is produced but the ČIŽP director can deliver his remarks in English at the latest on Wednesday 1 June and the project team will take these comments up in the final project results.

### 4.   Training program and training centre (RTA)

Training programmes

The training programmes were evaluated: the Strategic Planning training, the Train-the-trainers training, the General and Specialists enforcement techniques training. Much more participants were trained than originally planned, with very satisfactorily results. The Trained trainers participated successfully in the project’s trainers team. All 13 trained trainers were certified. The self-evaluations of the programmes showed that inspectors still have unsufficient knowledge on integrated approaches. All the modules were evaluated very positively by the participants, including the performance of the trained trainers.

Training and Methodological Centre (TMC)

A proposal for founding a Training centre has already been discussed in the Ministerial management meeting a few months ago, when the decision to establish CENIA was taken, in which educational activities are mentioned. The formal decision will be taken up in the TMC benchmark by Pavel Šremer. There is now a business plan for CENIA at the next Ministerial Management Meeting. This will include the decision to establish a training centre, without further background information. Next step is that there will be a proposal on the training centre, which will describe the activities and the budget. The project team and the ČIŽP hope that it will be rounded of in June. The establishment itself of the TMC provides the opportunity to arrange a bilateral project between the Netherlands and the Czech Republic, in which training methodology and training materials will be developed. It can only take place after establishment. The centre could then start with developed materials in January 2006. Mr. Slanec informed the meeting that the approval decision of the training centre was already taken in the Ministerial Management meeting in the framework of the establishment decision of CENIA. Mr Hradec has been given the task to work out the proposals with budget and tasks and responsibilities.

Petrtyl asks confirmation that the centre will have 2 staff members? Slanec replies that it will be organised in the present staffing framework and relevant tasks with an appropriate budget to start the development. Further funding is possible when other organisations will join.

In the evaluation of training programmes a quick SWOT analysis was performed. This SWOT will be summarised in the benchmark report on the final conference and will result in recommendations on the training centre in the final report.

Conclusion. The TMC is on the list of activities of the ČIŽP and CENIA. It has been agreed that a future ČIŽP training programme will make use of the training centre. The trained trainers will be involved whenever possible. They will have regular meetings.

5.   Informational networks (RTA)

Kramers finalised the information exchange benchmark, which was prepared in consultation with the twinning project on CENIA. Bakx:  it discusses the way information flows are organised in ČIŽP and between ČIŽP and other organisations. We come back to the minimum criteria forinspections, which for a proper implementation require a single database with environmental information, structured in an integrated way. The great number of previous small databasis, that existed until recently make it hard to fulfil the EU requirements. The benchmark had three main issues: 1) Development of monitoring ; 2) Information and data Exchange ; and 3) Accident prevention

Some recommendations in this benchmark are (without priority ranking)

- create one single environmental information database

- go beyond organisational borders, even if the law does not give the obligation to do that

- have a look at the legal framework to see how to use  or improve this framework; informal approaches to enforcement with other enforcement organisations may lead to improved (integrated) inspections.

- it is not completely clear whether safety management systems are included in the inspection activities or even in the law. This can be due to different use in terminology. Safety management systems are an EU requirement from the Seveso-II directive. It might be that the Czech law describes it as safety programmes and reports. It would be important to clarify whether full implementation has taken place. The directive was implemented by law No. 353/1999 Coll. On the prevention of major accidents caused by selected dangerous chemical substances and chemical preparations.

Other discussed topics were:

- Networking between the organisations at national and international levels requires manpower to further develop it. It is an investment that will not pay back in the first year. The higher quality and more production will come later.

- Proposals to law change on information exchange. They should be in line with the EU minimum criteria and the recommendations above. Discussions in the IMPEL network may lead to suggestion to do so. Also CENIA can play a role in defining the best direction of information exchange. It must be very clear that operational information exchange is on a practical level of the inspectors and that it is best not to make it the responsibility of the Ministry to organise that. They do not work with this information and it would make the information flows longer and less transparant. Mr Petrtyl is interested in the actual flows of information.

Additionally it can be said that the Minimum Criteria for environmental inspections is a recommendation, not a directive. Minimum criteria are not legally binding, but they are politically binding. The European Parliament will evaluate the success of the criteria within a few years. If they have been adopted too little, they are expected to become a directive after all. When the Minimum criteria speak about reporting, they generally focus on the reporting by inspectors, ‘internally’ in the organisations. However, co-ordination of the way of reporting in different enforcement organisations would help to make it clearer as an information source.

Šremer informed about the establishment of a Czech network for co-operation with the EU IMPEL network as follow-up of this project, using contacts and results o this project. This network includes most organisations involved in the area of environmental inspection and enforcement. The first meeting of this network was on 16th of May.

The final results on information exchange can be found on the website and on a CD that will be sent after project finalisation to all members of the Steering Committee.

  - Closure of the project (PL-MS)

The final conference was held in Benešov on 25 May, with as main topics:

  - Project results; and

  - 2) Sustainability of the project results. Slanec, Prášek and Mrs. Bauerova have spoken about the sustainability of the project results. The results will be written in the benchmark on the final conference.

Bauerova asks ČIŽP for taking note of the recommendations with care, as the project results are followed very closely from both the Czech and the EU sides.

Decisions

The project team promises to send the draft recommendations to all Steering Committee members. Everyone can comment before Thursday morning, 2 June, and the project team will decide whether the comments can be used. Comments by Mr Slanec can be taken up without any changes as an annex to the final report.

### Round of questions (PL-BC)

The Czech monitoring report on environmental twinning projects has been discussed in the Ministerial Management meeting. Results of the monitoring on this project on the fourth quarterly report, in which there is the recommendation on trainee’s self-evaluation , are misinterpreted. Questions that do not have the right quality are usually discarded. In one case, one question was eliminated because it was generally misunderstood. There is time to correct the report from the monitoring meeting through Martin Petrtyl before Friday 27 May.

### Closing of the meeting  and closure of the project (PL-BC and MS)

The last Steering Committee meeting was closed at 12.40 h. The chairman thanks all for their presence. He was happy with the feedback from the members. He thinks that the project has pushed the ČIŽP forward and hopes that the recommendations are taken up seriously. He would like to see the contacts continued.

The RTA thinks he has had 15 very interesting months. Sometimes he was not sure how to proceed. He can only change what he wants, not what others want. He found a ČIŽP with great potential. All discussions should lead to further development of that potential. Maybe in one or two years, he would be very happy to see that this development indeed has taken place. Many ČIŽP and other staff members have put a lot of energy in the project, including staff members of the head office. That all has already led to satisfactorily results. And still, there are challenges ahead and awaiting.