## List1
| Integrated and Planned Enforcement, CZ03/IB/EN/01 | 1 | MAR | 2004 | 2 |  | APR | 2004 | 3 |  | MAY | 2004 |  | 4 |  | JUNE | 2004 | 5 |  | JULY | 2004 | 6 |  | AUG | 2004 |  | 7 |  | SEPT | 2004 | 8 |  | OCT | 2004 | 9 |  | NOV | 2004 |  | 10 |  | DEC | 2004 | 11 |  | JAN | 2005 |  | 12 |  | FEBR | 2005 | 13 |  | MAR | 2005 | 14 |  | APR | 2005 | 15 |  | MAY | 2005 |  | 16 | JUN
| PLANNING ACTIVITIES | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66
| week number | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
| first day of the week | 8 | 15 | 22 | 29 | 4 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6
[9 empty] | 2004-05-01 | 2004-05-08 | K |  |  |  |  | (K) |  | K | 5 en 6-7 |  |  |  | K | K |  |  | (K) |  |  |  | 2004-09-28 |  |  |  | 2004-10-28 |  |  | 2004-11-17 |  | (K) |  |  | 2004-12-24 | [9 empty] | (K) |  |  |  | 2004-03-28 |  |  |  | 2004-05-01 | 2004-05-08 |  | (K)
1 | Work package 1: Inception
1a | Start up of the project
Opening project office RTA/PA | bar: 1 11 8
| Project launch | 1 11 8: 1.1
| Kick-off meeting | 6 16 12: I; 7 17 19: x; 10 20 10: 1.1
| Visit to inspectorate regions | 5 15 4: I; 6 16 12: x; 7 17 19: x; 9 19 3: 1.2 - W1a
| Pre-selection of trainers | 5 15 4: M - 1.6
1b | Review of linked activities
Reading results previous and running projects | bar: 5 15 4 to 7 17 19
| Discussion with RTAs of running projects | 5 15 4: I; 6 16 12: W1b1; 7 17 19: W1b2
| Plan for co-operation with Phare twinning project CZ02/IB/EN/03 | 7 17 19: 1.4
| Review report written | 7 17 19: x; 9 19 3: x - 1.3
1c | Compilation of an inception report
| Writing inception report | 13 23 31: X; 14 24 7: 1.5
2 | Work package 2: Strategic Plan Development
2a | Strategic plan development and implementation
| Support mission selected regions | 5 15 4: I; 6 16 12: X; 9 19 3: x; 10 20 10: 2a1
| Participatory workshop on framework conditions strategic plan | 11 21 17: I; 13 23 31: x; 14 24 7: x; 15 25 14: W2a1; 16 26 21: W2a1
| Supporting base level study on implementation of Minimum Criteria | 5 15 4: x; 6 16 12: x; 7 17 19: 2.1
| Management workshop CEI discussing draft plan + political follow-up | 30 40 27: I; 32 42 11: x; 35 45 1: W2a2
| Feedback workshops to 10 enforcement regions on strategic plan | 26 36 30: I; 28 38 13: x; 38 48 22: W2a3
2b | Training programme on the development of the strategic plan
| Training to develop strategic plan - seminar 1 | 9 19 3: x; 10 20 10: I; 13 23 31: x; 14 24 7: 2.2-W2b1
| Training to develop strategic plan - seminar 2 | 13 23 31: I; 15 25 14: x; 17 27 28: 2.2-W2b2
| Training to develop strategic plan - seminar 3 | 19 29 12: I; 22 32 2: x; 23 33 9: 2.2-W2b3; 24 34 16: x; 25 35 23: 2.2-W2b4
| Min. 15 staff trained in strategic planning | 28 38 13: x; 29 39 20: 2.3
| Offer strategic plan to decision makers | 28 38 13: x; 29 39 20: 2.4
| Start of implementation of the strategic plan | 43 53 27: x; 44 1 3: 2.5
2c | Study tour to the Netherlands
| Preparations | 23 33 9: x; 24 34 16: x; 41 51 13: 2.6
| Study visit (incl. report) | 41 51 13: X; 44 1 3: X; 45 2 10: 2.7; 47 4 24: X; 49 6 7: X
3 | Work package 3: Training programme
3a | Training needs assessment
| Setting agenda for study tour to Netherlands (see also activity 2c) | 34 44 25: x; 35 45 1: 3.1
| Interviews and discussions in enforcement regions | 21 31 26: I; 23 33 9: X; 25 35 23: W3a (P); 28 38 13: W3a - 3.1
| Setting training targets | 34 44 25: x; 35 45 1: 3.1
| Compiling report TNA | 34 44 25: x; 35 45 1: 3.1
3b | Common training and methodological centre
| Workshops defining goals, role, position, business plan of the training centre | 17 27 28: I; 25 35 23: I; 29 39 20: x; 30 40 27: W3b1; 31 41 4: X; 36 46 8: I (2x); 38 48 22: X; 39 49 29: W3b2/3; 41 51 13: W3b4; 42 52 20: I; 44 1 3: W3b5
| Prepared draft decision on establishment of training centre | 40 50 6: 3.2
3c | Training curriculum preparation
| 2 Workshops developing the curriculum and qualities of trainees | 28 38 13: I; 34 44 25: W3c1; 37 47 15: W3c2; 38 48 22: 3.3
Draw a list of training programme delegates | bar: 17 27 28
Develop training materials | bar: 31 41 4; 38 48 22
| Compilation of the trainers team | 18 28 5: 3.3; 38 48 22: X
3d | Execution of the training programme
| Carrying out a train-the-trainer training | 25 35 23: I; 26 36 30: X; 28 38 13: X; 29 39 20: 3.4-W3d1; 34 44 25: M - X; 36 46 8: 3.4-W3d2; 37 47 15: M - X
| Carrying out an enforcement techniques training programme | 43 53 27: I; 44 1 3: X; 46 3 17: X; 47 4 24: 3.4-W3d3; 49 6 7: I; 52 9 28: X; 53 10 7: 3.4-W3d4
| Implementattion of a mobile laboratories training programme | 54 11 14: I; 55 12 21: X; 56 13 28: W3d-p3
3e | Evaluation and reporting on training programme and official closure
| Workshop on evaluation of the training programme | 58 15 11: I; 59 16 18: X; 60 17 25: X; 62 19 9: X; 63 20 16: W3e1; 64 21 23: 3.5
| Writing of an evaluation report | 55 12 21: X; 56 13 28: M - X; 58 15 11: X; 59 16 18: M - X; 60 17 25: 3.6
| Workshop discussing main project results | 58 15 11: I; 63 20 16: W3e1
| Project closing | 58 15 11: I; 59 16 18: X; 60 17 25: X; 62 19 9: X; 63 20 16: W3e2; 64 21 23: 3.7
| Press conference | 58 15 11: I; 59 16 18: X; 60 17 25: X; 62 19 9: X; 63 20 16: W3e2; 64 21 23: 3.8
4 | Work package 4: Informational networks
4a | Development of monitoring of inspections and accident prevention
| 3 Workshops identifying present monitoring approaches | 31 41 4: I; 32 42 11: X; 34 44 25: W4a1; 38 48 22: I; 39 49 29: x; 41 51 13: W4a2; 45 2 10: I; 49 6 7: W4a3
| Developing a system for monitoring | 49 6 7: X; 55 12 21: X; 59 16 18: 4.1
Decision on adjustments in the monitoring system | bar: 60 17 25
Selection of 2-4 pilot regions | bar: 17 27 28
4b | Establishment of informational networks
| 3 Workshops establishing an environmental enforcement network | 16 26 21: x; 17 27 28: I; 18 28 5: x; 22 32 2: x; 23 33 9: W4b1; 24 34 16: x; 28 38 13: I; 29 39 20: x; 31 41 4: W4b2; 33 43 18: x - I; 34 44 25: x; 35 45 1: W4b3
| 2/3 Workshops containing programmatic network meetings | 37 47 15: I; 38 48 22: x; 39 49 29: x; 40 50 6: W4b4; 41 51 13: x; 44 1 3: I - X; 45 2 10: x; 46 3 17: W4b5; 47 4 24: 4.2; 51 8 21: I; 52 9 28: X; 53 10 7: X; 54 11 14: W4b6
4c | Information exchange within networks
| 3 Workshops on identifying information needs, users, gaps and drafting a plan | 23 33 9: I; 25 35 23: x; 26 36 30: W4c1; 37 47 15: x; 39 49 29: W4c2; 47 4 24: I; 49 6 7: x; 51 8 21: W4c3
| Drafting a plan to fill information an data exchange gaps | 52 9 28: X; 53 10 7: X; 55 12 21: 4.3
4d | Feedback to the regional and local level
| Production of a handbook on monitoring approach and network functioning | 51 8 21: x; 52 9 28: x; 53 10 7: x; 54 11 14: x; 55 12 21: 4.4
| Presentation of the handbook in workshops in 5 regions | 52 9 28: I; 55 12 21: x; 57 14 4: W4d; 58 15 11: W4d
5 | Work package 5: Management
Quarterly Report | bar: 13 23 31; 26 36 30; 39 49 29; 52 9 28; 66 23 6
| Final Report | [66 empty] | 5.6 | bar: 66 23 6
5a | Project management, RTA
Biweekly contact between CC-PL, CC-MS and RTA | bar: 2 12 15; 4 14 29; 6 16 12; 8 18 26; 10 20 10; 12 22 24; 14 24 7; 16 26 21; 18 28 5; 23 33 9; 25 35 23; 27 37 6; 29 39 20; 31 41 4; 33 43 18; 35 45 1; 37 47 15; 39 49 29; 41 51 13; 43 53 27; 45 2 10; 47 4 24; 49 6 7; 51 8 21; 53 10 7; 55 12 21; 57 14 4; 59 16 18; 61 18 2; 63 20 16; 65 22 30
| 5 Steering committee meetings and minutes | 12 22 24: 5.2; 28 38 13: 5.2; 41 51 13: 5.2; 54 11 14: 5.2; 65 22 30: 5.2
5b | Co-ordination with investment component
1 Approval letter of RTA | bar: 31 41 4
5c | Publications (newsletter, website, quarterly reports)
| 6 Electronic newsletters | 8 18 26: 5.1; 17 27 28: 5.1; 26 36 30: 5.1; 39 49 29: 5.1; 52 9 28: 5.1; 65 22 30: 5.1
| Project website updated monthly | 4 14 29: 5.3; 8 18 26: 5.3; 12 22 24: 5.3; 17 27 28: 5.3; 23 33 9: 5.3; 26 36 30: 5.3; 30 40 27: 5.3; 34 44 25: 5.3; 38 48 22: 5.3; 44 1 3: 5.3; 48 5 31: 5.3; 52 9 28: 5.3; 57 14 4: 5.3; 61 18 2: 5.3; 64 21 23: 5.3
| Project website maintained quarterly | 4 14 29: 5.3; 17 27 28: 5.3; 30 40 27: 5.3; 44 1 3: 5.3; 57 14 4: 5.3
| CD with project results | 65 22 30: 5.4
5d | Accountant
| 1 accountant report | 66 23 6: 5.5
5e | Translations
Interpretation training sessions | bar: 48 5 31; 53 10 7
Translation of benchmarks
[11 empty] | K |  |  |  |  | (K) |  | K |  |  |  |  | K |  |  |  | (K) | [12 empty] | (K) | [12 empty] | (K) | [10 empty] | (K)
W1a, etc. | Workshop number | 2 12 15: Mission expert(s); 7 17 19: RTA or MS-PL Leave
1.1, 1.2, etc. | Benchmark | 7 17 19: PA Leave
x | Work at this topic | 2 12 15: Mission RTA/PA; 7 17 19: AC-PL or PC Leave; 13 23 31: VERSION 2004-05-18
I | Invitation (and agenda) to be sent | 1 11 8: Q/F; 2 12 15: Quarterly / Final report; 7 17 19: Other national holiday weeks
M | Meeting | 7 17 19: Double or more Leave / holidays
K | This week Koen is in CR; (K) = still to be confirmed