# Quarterly Report 1

# 8 March – 31 May 2004

Report prepared by:

| Pavel Šremer | Koen de Kruif |
| --- | --- |
| ČIŽP International Affairs Department | International Projects Leader |
| Czech Environmental Inspectorate | DCMR Environmental Protection Agency |
| Na Břehu 267/1a | PO Box 843 |
| 190 00 Prague 9 | 3100 AV Schiedam |
| Czech Republic | Netherlands |
| Tel: +420 222 860 327 | Tel: +31 10 246 8550 |
| Fax: +420 283 892 662 | Fax: +31 10 246 8589 |
| sremer@cizp.cz | kmk@dcmr.nl |

Date submitted: 7 July 2004

Identification

| Twinning Project No.: | CZ2003/IB/EN-01 |
| --- | --- |
| Report No.: | 1 |
| Period covered by the report: | 8 March – 31 May 2004 |
| Submitted by: | Pavel Sřemer and Koen de Kruif |

- Background

2.1	Introduction

The overall objective of the CZ03/IB/EN/01 Twinning Project is to acquire the ability to take on the obligations of membership of the European Union and the acquis communautaire.

The project has the objective to strengthen environmental protection through integrated and planned approach to enforcement of environmental laws at central enforcement institutional level and also regional level of state administration. Particular attention will be paid to clear distribution of competencies, co-operation between responsible authorities, training and investment in planning capacities.

| Work Package 1: | Inception Phase |
| --- | --- |
| Work Package 2: | Strategic plan development: Integrated inspection approach |
| Work Package 3: | Training programme |
| Work Package 4: | Informational networks |
| Work Package 5: | Management |

2.2	 Guaranteed results from the Enforcement Project

The contents of this Twinning project will make a significant contribution to achieving some of the wider objectives of the Czech Environmental Policy and will lead to the following long-term results:

- EU Minimum Criteria for environmental  inspections are fulfilled at central, regional and local level

- New strategic plan for the Czech Environmental Inspectorate and trained staff for strategic planning implemented.

- New network of different state administration institutions for environmental enforcement  established.

- Better equipment for monitoring in relation to inspections and accident prevention (stabile and  mobile labs  and trained staff ) resulting in better CEI capability of action. Providing for better information of public and state administration inspectors by means of up to date IT.

- Integrated approach of different state administration institutions (Seveso II Directive, GMO Directive, Water Framework Directive, Regulation on Control of Transfrontier Shipments of Wastes) and  at different levels (esp., Seveso, IPPC)

- Common training and methodological center for training of CEI inspectors as trainers and regional/local officers at CEI and training of inspectors from different institutions for enforcement of Seveso-II Directive, GMO Directives, IPPC Directives, and the Water Framework Directive, fully co-ordinated with developments in IMPEL trainings on the Regulation on Control of Transfrontiers Shipments of Wastes.

- Inspectorate will have used the experiences of the British-Czech Project on training of CEI inspectors. This project will have enlarged the trainers team with members from other bodies (regional and local offices) and other cooperating institutions together with CEI inspectors. The aim is spreading of cooperative spirit and also trainers will be trained in implemented Directives.

- After training inspectors will have the qualifications to implement the relevant directives in an integrated and planned way.

- The results will have been dissiminated to all different inspectorates at local, regional and national level.

- The implementation of the Seveso-II Directive, GMO Directives, IPPC Directive, the Water Framework Directive, and the Regulation on Control of Transfrontier Shipments of Wastes has started.

- A secured relationship with the management and STEs of the Phare CZ02/IB/EN/03 IPPC project on exchange of experts, experience and common use of each other’s results.

3.	Twinning activities during the reporting period

During the quarter there have been activities undertaken for the work packages 1, 2 and 5.  Set out below are descriptions of these activities, results to date and progress against achieving benchmarks.

3.1	Work Package 1 – Inception

Further specification of the work programme by involving the regional enforcement institutions and thorough review of the previous and running bilateral and multilateral projects. The activities in this package focus on the setting up of the project and publicising its start. They comprise three distinct activities: visits to and discussions with all involved institutions; a visit to each of the 10 inspectorate regions; review of linked activities, including other Phare projects; and drafting a report on the inception phase. The missions envisaged by the covenant were successfully executed in this quarter.

| Activity number and description | Current Status |
| --- | --- |
| 1a Start up of the project - An offical project launch was held in Prague in the first week of the project. Representatives off almost all introduced enforcement and other institutions attended the launch. From the Netherlands the deputy mayor of Ridderkerk and member of the board of DCMR, mr. Van Andel, attended the launch. A press release on the project was issued. - Visits to all the involved institutions to detail the appointments made in the covenant and discuss with these institutions the expected inputs in a Kick-off meeting. The RTA, together with the Czech project leader, contacted and visited at the central level high level representatives (up to and including 3 deputy Ministers) of the Ministry of Environment, the Fire Brigade, the Ministry of Health, the IPPC Agency, the Czech Ecological Institute, the Czech Police, the Customs Office and the Occupational Safety authorities. The Kick-off meeting with representatives of these organisations was combined with the first Steering Committee meeting. - Visit to the enforcement institutes in the 10 inspectorate regions. A visit of the RTA and the Czech project leader to each of the 10 regional offices of the Czech Environmental Inspectorate was organised to meet and involve the management of the different enforcement organisations in these regions in the project activities. These inspectorate regions are: - Prague - Havlickuv Brod - Brno - Olomouc - Ostrava - Hradec Kralove - Liberec - Usti nad Labem - Plzen - Ceske Budejovice In the regional meetings, which all together were addressed by 104 participants, the project was presented and expected results were discussed. There were opportunities for the representatives of regional authorities, local authorities, hygiene offices, Czech Environmental Inspectorate, Trade Inspectorate, Fire Brigade, Police, Occupational Safety Inspectorate and the regional representatives of the Ministry of Environment to interact with the RTA, the Czech project leader and with each other. - Present the EU minimum criteria for environmental inspections and discuss the expected project results and the way the enforcement institutes expect to use the results beyond the framework of the project. During the visit to the Inspectorate Regions this activity was included in the program and carried out. - Pre-selection of potential trainers A first selection of potential trainers within the Czech Environmental Inspectorate (CIZP) has been made by the RTA together with the Czech project leader, the Czech project coordinator and staff of the Inspectorate’s Personnel Department. This list is now being completed within CIZP including names of representatives of other enforcement institutions. | Done Done Done Done Done Benchmark 1.6 (list of pre selected trainers) to be drafted after completion of the list within CIZP |
| 1b Review of linked activities - Meetings and discussions took place with RTA’s and project leaders of the following related projects: - Reinforcement of IPPC implementation (CZ02/IB/EN/03); - Environmental Information and Management system – CENIA (CZ03/IB/EN/02) - The IMPEL project “Developing capacity in implementation and enforcement through the AC IMPEL network” concerning an institutional review of the Czech Environmental Inspectorate The results of relevant previous and the running bi- and multi lateral projects have been read and where relevant they have been discussed with the RTAs running Phare twinning projects. - With the RTA of the Phare2002 twinning project on Reinforcement of IPPC implementation the common activities and the way they will be organised in co-operation have been discussed and agreed upon. | Done – Benchmark 1.3 on linked activities currently being drafted Done – Benchmark 1.4 currently being drafted |
| 1c Compilation of an inception report - The relevant elements of other projects, the present experience in the regions and the more detailed requirements for sustainability of project results will be written down in an inception report. This inception report will focus the work on procedures and the training needs assessment. The inception report should be seen as a more detailed work programme for the tasks ahead. | Benchmark 1.5 (Inception report) is currently being drafted |

|  | Benchmarks Work Package 1 | Status |
| --- | --- | --- |
| 1.1 | One project launch and one kick-off meeting | Done |
| 1.2 | One series of visits to the different enforcement regions | Done |
| 1.3 | One review report on the analysis of linked activities and confirmation of procedures to be used in work packages 2, 3 and 4 | Not complete – due Q2 |
| 1.4 | One plan for co-operation with the RTA and experts in Phare Twinning 2002 on IPPC project (CZ02/IB/EN/03) | Not complete – due Q2 |
| 1.5 | One inception report | Not complete – due Q2 |
| 1.6 | One list of pre-selected staff of enforcement institutes to be trained as trainers | Not complete – due Q2 |

3.2	Work Package 2: Strategic Plan development: Integrated inspection approach

The objective of this work package is to develop a stategic enforcement plan and to write this plan. Training on this topic will be provided and CEI-staff together with staff of other involved institutions will be supported in the plan development. The plan development will be an iterative process, using input from all layers in the inspectorate organisation. In the first quarter the support mission has been carried out and the participatory workshops as well as the training programme have been prepared. Time has been spent on discussing strategy needs at the highest level of the CIZP. Due to changes in the CIZP management after tendering the Phare project a change of focus towards the project and its objectives has taken place. This led to more time consuming efforts to involve inspectorate staff and commit the right persons.

A prior consensus between the RTA and the CIZP management to present the project’s strategic planning part to the Minister was mentioned from the CIZP side at a later stage to be a misunderstanding.

The work package also includes a study tour to the Netherlands, giving insight in the strategy of enforcement there and the way in which it actually works. So far no relevant activities have been executed for this part of the project.

| #### Activity number and description | Current Status |
| --- | --- |
| 2a Strategic Plan development and implementation A support mission has been carried out involving the Chief Inspectors of all the 10 CIZP inspectorate regions. This mission took place in Prague in the form of a workshop including carrying out a preliminary SWOT analysis. Within the Czech Environmental Inspectorate all relevant meetings of regional and central level heads of department and their deputies were addressed, informing the overall inspectorate management about the project. At the CIZP Head quarters in Prague the project was personally discussed in detail with all relevant heads of department. - Workshops in each of the 10 enforcement regions gathering information and opinions as basis for defining the conditions and prerequisites that should be taken into account in the development of a strategic plan on integrated inspections and the commitment of the enforcement institutions in training programmes. A series of participatory workshops to each of the 10 CIZP regions has been prepared. These workshops will be carried out in quarter 2 and will involve staff at the work level in the strategic plan development. - Decide about implementation of the in 2b developed strategic plan (this is a process rather than a decision in one workshop) - Support to a base level study on the implementation of the EU Minimum Criteria for environmental inspections, to be written by the CIZP. Due to discussions on CIZP staffing of the project this activity is foreseen to take place in the second quarter of the project. - Feedback on progress and results to staff in one workshop in each of the 10 regional inspectorates | Prepared – Due Q2 Due Q3 Due Q2 Due Q3 |
| 2b Training programme on the development of the strategic plan As the representative of the CIZP to co-ordinate the development of the strategic plan the Czech project leader was appointed. He will be responsible for the completion of the final plan. A group of delegates at the management level from different enforcement institutions (Fire Brigade, Customs Office, Police, Occupational Safety authorities, Health authorities, CIZP) has been selected and nominated by their organisations to participate in the training workshops on strategic planning. - Three to four training seminars to prepare, develop and write the strategic plan The seminars have been planned and prepared in the first quarter of the project and will be carried out in the second quarter. - Offer the plan to the strategic decision makers in 2a | Prepared – Due Q2 Due Q3 |
| 2d Study tour to the Netherlands Due to discussions with(in) the CIZP concerning staff participation in the project activities the prelimary project planning was adjusted, causing that the study tour now is foreseen to take place in the fourth quarter of the project. - Prepare a study visit for maximum of 6 delegates from CIZP, the RTA and the PA to the Netherlands - Offer a programme giving insight in the strategy of enforcement in the Netherlands and the way it actually works in practice - Discuss the experiences that are useful for the Czech situation and offer potential in Czech Republic | Due Q3 Due Q4 Due Q4 |

|  | Benchmarks Work Package 2 | Status |
| --- | --- | --- |
| 2.1 | One base level study on the implementation of the EU Minimum Criteria for environmental inspections delivered by CEI. | Due Q2 |
| 2.2 | Three executed training seminars on strategic planning. | Due Q2 |
| 2.3 | Min. 15 trained staff in strategic planning from different environmental enforcement institutions. | Due Q2 |
| 2.4 | One developed strategic plan. | Due Q3 |
| 2.5 | One implementation of the strategic plan started. | Due Q4 |
| 2.6 | One study tour prepared, the participants selected, and tour executed. | Due Q4 |
| 2.7 | One study tour report. | Due Q4 |

  - Work Package 3: Training programme

The objective of this work package is the preparation of a training curriculum and training materials and to execute a full training programme on it. In a final workshop the training results will be evaluated and presented. This workshop will include the project closure and a press conference.

The work package will include a training needs assessment and will also prepare a draft decision for establishing a training and methodological centre, on training the trainers for this centre and on carrying out a training programme. The training programme will cover a train-the-trainer programme, an enforcement techniques programme and training for the use of mobile laboratory equipment. Around 12 trainers and 40 other staff members will be trained.

On completion an evaluation report on the training will be prepared.

The idea of setting up a training center has received support from two deputy Ministers and has been presented to the Minister of the Environment by the CIZP management. The Minister is awaiting further details and proposals from CIZP in the second quarter of the project. So far the CIZP management has not forwarded a proposal for coordination of its initiative with the project.

| Activity number and description | Current Status |
| --- | --- |
| 3a Training needs assessment - Review of the results of the Phare twinning project 1998 on ‘Strengthening the institutional and regulatory capacity in the environmental sector in the Czech Republic” - Review the TNA of the Phare 2002 project on ‘Reinforcement of IPPC’ - Interviews and discussions in selected enforcement regions - Processing all information and writing a TNA report | Due Q2 Due Q2 Due Q3 Due Q3 |
| 3b Common training and methodological centre - Defining the goals of a training centre - Prepare actions to make it politically and financially stable: contact relevant sponsors, find a legal position for the centre, find political commitment - Define a methodological basis for the centre and link this with the strategic plan - Compile a draft business plan for the centre - Define the role of the centre in local, regional, national and international networks - Establish the centre | Due Q4 Due Q4 Due Q4 Due Q4 Due Q4 Due Q5 |
| 3c Training curriculum preparation - Define the training programmes, the curriculum and the required results - Define the required qualities of the delegates to the programmes - Decide on the list of delegates to the training programme - Develop training materials | Due Q4 Due Q4 Due Q4 Due Q3 |
| 3d Execution of the training programme - Execute the train-the-trainers programme - Execute the enforcement techniques programme - Execute the mobile laboratories programme | Due Q3-5 Due Q4-5 Due Q5 |
| 3e Evaluation training programme and official closure - A workshop on evaluation of the training programmes - An Official closure of the project with presentations on the project results - A project results press conference | Due Q5 Due Q5 Due Q5 |

|  | ##### Benchmarks Work Package 3 | Status |
| --- | --- | --- |
| 3.1 | One training needs assessment, including the setting of specific training targets and the agenda of the study tour for Work Package 2. | Due Q3 |
| 3.2 | One formal decision on the establishment of a common training and methodological centre for training of inspectors from CEI and other enforcement institutions. | Due Q4 |
| 3.3 | One training curriculum for a training programme for inspectors of enforcement institutions. It includes the compilation of the team of Czech trainers. | Due Q4 |
| 3.4 | Three training programmes executed: the train-the-trainer programme (max. 12 delegates), and the enforcement techniques programme (max. 40 delegates). | Due Q3-5 |
| 3.5 | One workshop with presentations on the results of the training programme. | Due Q5 |
| 3.6 | One evaluation report on the results of the training programme. | Due Q5 |
| 3.7 | One official project closure. | Due Q5 |
| 3.8 | One press conference. | Due Q5 |

  - Work Package 4: Informational networks

The overall aim of this work package is to improve the co-operation between the responsible authorities at local, regional and central level and to open the possibilities for communication and data exchange between these authorities and relevant experts of other institutions within and outside the Czech Republic.

The activities will focus on development of monitoring and inspections and accident prevention, on the establishment of informational networks, on information exchange within networks and on giving feedback of the work to the regional and local level.

| Activity number and description | Current Status |
| --- | --- |
| 4a Development of monitoring and inspections and accident prevention - Selection of 2-4 pilot regions,that will in first instance participate in the development of an improved monitoring approach, taking into account the high workload of all regional and local enforcement institutions. - A workshop on identification of the different administrations, their present activities and their used monitoring approaches. - A discussion on the possibilities for improvement of the present monitoring and assessment system. - Development of an improved system for administration and assessment of enforcement activities. | Due Q2 Due Q3 Due Q4 Due Q5 |
| 4b Establishment of informational networks - A discussion on the function and use of informational networks. - Definition of the role and targets of an informational network and how the Czech Informational network should work in practice. - Organise meetings for partners in the network on specific themes to stimulate further development and use of the network. | Due Q2-3 Due Q2-3 Due Q4-5 |
| 4c Information exchange within networks - Identification of the information exchange needs. - Identification of the gaps in the tools presently available to support information exchange and how to bridge these gaps. - Drafting a plan how to fill in gaps in the information exchange system and forward these to the decision makers. | Due Q3 Due Q3-4 Due Q5 |
| 4d Feedback to the regional and local level - Preparation of a handbook containing information on adjusted monitoring approach, the operation of the enforcement network and possibilities for information exchange. - Present the handbook and additonial expertise on the use of networks to combinations of regions. (max 5 meetings). - Information to all regions on an additional day of the 3e conference on evaluation of the training results. | Due Q5 Due Q5 Due Q5 |

|  | Benchmarks Work Package 4 | Status |
| --- | --- | --- |
| 4.1 | One proposed system for monitoring of activities in relation to inspections and accident prevention. | Due Q5 |
| 4.2 | One established network between different institutions for environmental enforcement. | Due Q4 |
| 4.3 | One plan for filling in gaps in the present system for information and data exchange. | Due Q5 |
| 4.4 | One handbook on the developed network, possibilities of information supply and exchange and the monitoring approach developed and presented to the regions. | Due Q5 |

  - Work Package 5: Management

The purpose of this Work Package is to ensure overall co-ordinated management of the project, and wide dissemination of project outputs.  In close co-operation with the beneficiaries, communication and information networks will be used to support the overall aim of the project. Amongst the main activities are the execution of the meetings of the Steering Committee to ensure that the project continues to run to time, budget and quality.

| Activity number and description | Current Status |
| --- | --- |
| 5a Project co-ordination - Covenant preparations - Five Steering committees and progress discussions The Dutch PL has attended the Steering Committee meeting. - Daily presence of RTA and involvement in CIZP and enforcement institutions - Project planning and reporting (quarterly reports and financial reports) The RTA and Dutch PL have regular communication on the progress of the work. Together, they do the planning and the reporting. | Done SC 1 meeting completed Done Done |
| 5b Co-ordination with investment component - Supervising the process of investments Co-ordination of the investment part of the project with activities in this field by the CIZP is difficult. The CIZP management has taken action in this area towards the Ministry without prior coordination with the RTA. So far the consequences for the co-financing arrangements of the Czech Republic are not fully clear. - Giving advice on the use of the equipment in the framework of the enforcement strategy. The CIZP management has requested the RTA to positively advice on an (not specified) investment proposal towards the Ministry of Environment. The RTA has referred to the earlier appointment of March 2004 between the CIZP management, the Ministry and the EC delegation to link the RTA’s opinion on an investment proposal to the decided strategic plan. | Possible bottle-necks in co-financing by Czech Republic |
| 5c Newsletter, CD and website - Publications of electronic newsletters - Setting up and maintenance of a website A website for the project was constructed and is being maintained. At present it contains basic information both in English and in Czech on the project. Links to the IPPC and CENIA projects have been established. Benchmarks, mission agendas, project documentation and other useful information will be available. The site is an integral part of the CIZP website and can be found at http://www.cizp.cz/ under the heading ‘International’, drop down menu ‘Twinning project’. - Publication of all relevant materials, handbooks and training curriculum on CD | Due Q2 Website set up Due Q5 |
| 5d Accountant - Preparations for an accountant report, to accompany the final invoice | Due Q5 |
| 5e Translations - Translation of written materials from English to Czech and vice-versa A pool of translators/interpreters has been contracted under a framework contract which sets out pay rates and general terms. Each translation or interpretation activity is contracted by a specific contract. Three documents concerning strategy and integrated inspections have been translated. The PA has translated invitations and workshop materials and interpreted during meetings and workshops. | Progress is in line with the covenant |

|  | Benchmarks Work Package 5 | Status |
| --- | --- | --- |
| 5.1 | Six electronic project newsletters | Due Q2-5 |
| 5.2 | Five sets of minutes/action points from the steering committee meetings | Draft minutes SC1 under translation, expected inQ2 |
| 5.3 | One project website, updated monthly, maintained four times a year | Website set up in Q1, maintenance due Q 2-5 |
| 5.4 | One CD with project results | Due Q5 |
| 5.5 | One accountant report | Due Q5 |
| 5.6 | One approved final report | Due Q5 |

- 4.	Financial Statement

Spending under this Twinning project in the first quarter of implementation was in line with the Covenant budget plan. One side letter (without financial aspects) has been notified to the CFCU and the EC Delegation.

| Activities | Budget (Euro) | Total spent | Percentage of budget spent |
| --- | --- | --- | --- |
| 1: Inception | € 6.482,00 | € 4.743,-- | 73,17% |
| 2: Strategic plan development | € 22.336,00 | € - | - |
| 3: Training programme | € 48.324,00 | € - | - |
| 4: Informational networks | € 19.714,00 | € - | - |
| 5: Management | € 294.343,96 | € 75.961,74 | 26,56% |
| 6: Contingency | € 8.800,00 | € 996,38 | 11,32% |
| Total | € 399.999,96 | € 81.701,12 | 20,43% |
| Total budget available | € 400.000,00 |  |  |

- 5. Assessment of activities

  - The principal objectives of the first quarter have been the start up of the project, the strengthening of links between the project team and Czech state authorities and laying a foundation for the strategic discussions within the CIZP.

  - During the round tour of the regions there was active participation by delegates of the Regional Authorities, Local authorities, Regional Hygiene Offices, CIZP, Regional representatives of the Ministry of the Environment, Police, Fire Brigade, Customs Office, Trade Inspectorate and Occupational Safety Inspectorate.

  - In the discussions during the tour it became clear that most organisations involved lack strategic approaches. At least as far as the CIZP is concerned this is in line with the (orally provided) conclusions of the consultants in the presently running IMPEL project “Developing capacity in implementation and enforcement through the AC IMPEL network” concerning an institutional review of the Czech Environmental Inspectorate.

  - It also showed that training facilities are available in several organisations and that the Fire Brigade has mobile laboratories that may provide the needs foreseen under the investment part of the project. This should be investigated by the CIZP. The involved organisations showed a positive attitude towards co-operation.

  - At the regional level it was strongly felt that information exchange in the regions is at an acceptable level, but that there is a gap in information exchange between the central and the regional levels. Also management support for strategic planning was considered crucial for success of the project in this area. The staff from the regional offices felt a lack of methodological support and information supply from the central office, complicating the daily work, causing different approaches, loss of strength as an inspectorate and reduced motivation of staff.

  - The progress of the project activities has been influenced by the discussion with the CIZP management on involvement of CIZP staff in the project activities. The same goes for the position of the CIZP management towards the project objectives. So far the director of the CIZP did not express his unconditional support towards the project objectives. The director shows a double attitude. Critical, anyhow not unambiguously supportive, about the project towards his staff and in a way supportive in his relation with the twinning advisor. This results in a careful attitude of some CIZP staff towards project involvement. It also creates confusion, information crucial for the project is not provided on a regular basis (it has to be found by the project staff itself, like concerning the investment component, crucial changes in legislation taking place, developments in the political context) and the amount of time needed to fulfil the project objectives is relatively high.

  - It was noted that the relationship between the top of the CIZP and a number of stakeholders (especially in the Ministry of the Environment) is not at the best level possible. Some of the communication lines between these seem to suffer from interference.

  - In discussions with CIZP staff it was expressed that training concerning GMOs as well as SEVESO II has been provided previously. Training on these topics would preferably have the form of intercolleague exchange of practical experience in workshop form.

  - Of (major) influence on the project results can be the fact that the present CIZP management wants to wait for the results of an experiment in integrated inspection approaches that is taking place. This approach was introduced after reconsidering a number of organisational developments concerning integrated inspection approaches based on the IPPC directive and supportive to the EU minimum criteria for environmental inspections. Some organisational arrangements concerning integrated approaches have been built down in that context. Basic information on integrated inspection approaches translated into Czech has been provided to the CIZP management by the RTA. It is unclear whether this information has created any action.

  - CIZP staff have worked very quickly to set up a functioning website within the first quarter. This should prove to be an effective mechanism for disseminating project information and to support and promote the strategic planning.

  - The investment component of the project has given rise to a number of discussions and the quality of its preparation by the CIZP seems a continuous point of attention. Under the present circumstances it can be questioned whether the foreseen term to provide the Technical Specifications (September 2004) will be realised.

  - It should once more be emphasized that the quality of the end result of the project will for a large part be determined by the level of support of the Czech project partners to the project objectives and to maintain good communication and coordination with the project.

6.	Conclusions

  - Two Duch PL missions and one mission by the RTA/PA have been executed, which is in accordance with the mission plan.

  - Project management and administration arrangements have been put in place for managing the budget, missions and benchmarks.

  - Of the six benchmarks programmed for work package 1, two have been completed and the remaining four are being drafted.  One steering committee has been completed; one project launch has been completed.

  - Activities and benchmarks for work package 2 (participatory workshops and strategic training workshops) have been prepared.

  - A project website has been set up.

  - Expenditure on work package 1 has been completed.

  - An internal CIZP project team has been established. Relations within the project team, and with partner organisations such as the Fire Brigade, the Customs Office, the Police, regional authorities, etc. have been developed.

  - Serious points of concern occur in the area of CIZP management commitment towards the project objectives and to the communication between the CIZP management and the project management. This includes CIZP activities and initiatives concerning the investement component.